## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOBARDHANPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER PINGLA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/12825 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation / Augmentation of existing Gobardhanpur PWSS within Pingla Block under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division |  | ORD/001011/2021-2022 | 530/MD | 21/03/2022 | 31/03/2022 | RISHAN ENGINEERING CONSULTANCY | 2.95 | 0 | 0 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOBARDHANPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER PINGLA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/12825 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000076/2022-2023 | 93/MD | 10/01/2023 | 10/01/2023 | Resource Division | 12.24 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOBARDHANPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER PINGLA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/12825 | Augmentation | Electric quotation bill for Tw no-III of Gobardhanpur water supply scheme.(Ref consumer ID-204049772) |  |  | BILL/02683/2023-2024 | BP-2023-24-274 | 12/10/2023 | 12/10/2023 | WBSEDCL | 4.65 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOBARDHANPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER PINGLA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/12825 | Augmentation | Electric quotation bill for Tw No-IV of Gobardhanpur water supply scheme (Ref Consumer ID-204049773) |  |  | BILL/02685/2023-2024 | BP-2023-24-273 | 12/10/2023 | 12/10/2023 | WBSEDCL | 2.71 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOBARDHANPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER PINGLA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/12825 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOBARDHANPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER PINGLA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001595/2022-2023 | 478/W/MMD | 20/03/2023 | 10/03/2025 | DIPALI CONSTRUCTION | 22.98 | 0 | 0 | 35
6 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOBARDHANPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER PINGLA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/12825 | Augmentation | Sinking of Tube well (2nd), Construction of Pump House & Laying rising main pipeline for Augmentation of Gobardhanpur PWSS in Pingla block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | ORD/000329/2024-2025 | 3572/MD | 06/12/2024 | 02/10/2025 | ARNAB PATRA | 12.74 | 0 | 0 | 50
7 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOBARDHANPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER PINGLA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/12825 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary wall with allied work for Augmentation of Gobardhanpur & its adjoining mouzas W/S Scheme in Pingla Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | ORD/000504/2022-2023 | 2517/MD | 09/12/2022 | 24/01/2026 | DIPAK KUMAR BAKLY | 159.48 | 0 | 0 | 10
8 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOBARDHANPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER PINGLA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/12825 | Augmentation | Construction of 5.40 X 3.60 Mtr. Switch Room cum Chlorine Room with W.C. & Bath for Augmentation of Gobardhanpur W/S Scheme in Pingla block within Kharagpur Sub-Division under Midnapore Division, PHE Dte. (Considering G.L. 1950 mm below Road Level) {Type-B}. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | ORD/000825/2023-2024 | 706/MD | 12/03/2024 | 02/03/2026 | CHANDAN YADAV | 7.21 | 0 | 0 | 50
9 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOBARDHANPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER PINGLA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/12825 | Augmentation | Construction of approach road (concrete road) for Augmentation of Gobardhanpur PWSS Head Work Site at Ratrapur in Pingla Block within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | ORD/000442/2024-2025 | 348/MD | 30/01/2025 | 26/12/2025 | M/S BAKLY CONSTRUCTION | 6.1 | 0 | 0 | 1
10 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOBARDHANPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER PINGLA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/12825 | Augmentation | Providing and installation of Submersible pumping machineries and other allied electromechanical works at Newly sunk Tube well (Relacement) at Pump House-2 under Gobardhanpur water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist.:- Paschim Medinipur | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001865/2024-2025 | 788/W/MMD | 24/02/2025 | 23/08/2025 | M/S. SAJAHAN CHOWDHURY | 14.21 | 0 | 0 | 0
Total | [13 empty] | 245.29 | 0 | 0