## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SATKUI TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/12826 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation / Augmentation of existing Satkui PWSS within Kharagpur-I Block under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division |  | ORD/001009/2021-2022 | 519/MD | 17/03/2022 | 27/03/2022 | SIRCON ENGINEERING SERVICES | 2.24 | 0 | 0 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SATKUI TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/12826 | Augmentation | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations under (1) Augmentation of Keshiary & its adjoining mouzas W/S Scheme within Keshiary block & (2) Augmentation of Satkui & its adjoining mouzas W/S Scheme within Kharagpur-I block in Paschim Medinipur District through Jadavpur University. | AE Kharagpur Sub-division |  | ORD/000617/2022-2023 | 471/MD | 15/02/2023 | 01/03/2023 | JADAVPUR UNIVERSITY | 9.56 | 0 | 0 | 100
3 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SATKUI TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/12826 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SATKUI TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001610/2022-2023 | 533/W/MMD | 20/03/2023 | 16/09/2023 | P.K.ENGINEERING | 22.78 | 0 | 0 | 45
4 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SATKUI TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/12826 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000091/2022-2023 | 182/MD | 16/01/2023 | 16/01/2023 | Resource Division | 15.15 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SATKUI TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/12826 | Augmentation | QUOTATION FOR NEW POWER SUPPLY FOR SAKUI W/S SCHEME , T W NO 02, CONSUMER ID 204030395, SCHEME CODE SM/12826 , NIMPURA CCC WBSEDCL |  |  | BILL/01613/2023-2024 | BP-2023-24-130 | 19/07/2023 | 19/07/2023 | WBSEDCL | 0.56 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SATKUI TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/12826 | Augmentation | Laying of pipeline supportive to retrofitting to accommodate FHTC including supplying, laying, fitting, fixing of 15mm dia. NB PVC (Sch-80)/20mm dia. HDPE (PE-100, PN-16) pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM for Augmentation of Satkui & its adjoining mouza W/S Scheme within Kharagpur-I Dev. block under Kharagpur Sub-Division of Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000100/2023-2024 | 2475/MD | 14/07/2023 | 28/07/2023 | ARNAB PATRA | 7.07 | 0 | 0 | 100
7 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SATKUI TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/12826 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall & Construction of 200 CuM Capacity OHR with 20 m Staging height for Augmentation of Satkui PWSS in Kharagpur-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | ORD/000520/2022-2023 | 2572/MD | 16/12/2022 | 17/02/2026 | DULAL CHANDRA DAS | 196.05 | 0 | 0 | 42
8 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SATKUI TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/12826 | Augmentation | Sinking of 250 X 150 mm dia. X 215 Mtr. Depth deep tube well, Construction of Pump House & Boundary wall of 3rd tube well site and interconnection of 3rd tube well with distribution line and repair of OHR & Pump House-I for Augmentation of Satkui W/S Scheme within Kharagpur-I block under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000515/2024-2025 | 669/MD | 10/03/2025 | 24/05/2025 | M/S CHOWDHURY CONSTRUCTION (NEW) | 21.62 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SATKUI TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/12826 | Augmentation | Route survey & way leave permission along & across of National Highway under Augmentation of Satkui PWSS under Kharagpur Sub-Division of Midnapore Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000489/2024-2025 | 523/MD | 19/02/2025 | 12/03/2025 | PIONEER SURVEYORS | 9.11 | 0 | 0 | 0
Total | [13 empty] | 284.15 | 0 | 0