## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SHANRPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER DEBRA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/12827 | Augmentation | Restoration of pipe line damaged due to construction of roads & Construction of Sluice Valve Chamber within Shanrpur & its adjoining mouzas (Gayeshpur, Kolkuria, Bhuiabasan, Bar Bhuiabasan, Bhainagar etc.) W/S Scheme at Debra Block under Kharagpur Sub Division within Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division |  | ORD/000478/2021-2022 | 2172/MD | 17/12/2021 | 31/01/2022 | UCON | 42.21 | 26.12 | 61.86 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SHANRPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER DEBRA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/12827 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation / Augmentation of existing Shanrpur PWSS within Debra Block under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division |  | ORD/001008/2021-2022 | 518/MD | 17/03/2022 | 27/03/2022 | SIRCON ENGINEERING SERVICES | 2.62 | 2.44 | 93.11 | 100
3 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SHANRPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER DEBRA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/12827 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SHANRPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER DEBRA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001597/2022-2023 | 480/W/MMD | 20/03/2023 | 16/09/2023 | PURUSHOTTAM ENTERPRISE | 10.98 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SHANRPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER DEBRA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/12827 | Augmentation | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 200 Cum OHR (Intze type with Raft foundation) & under JJM with allied work for Augmentation of Shanrpur PWSS in Debra block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division |  | ORD/000302/2024-2025 | 3398/MD | 25/11/2024 | 24/05/2025 | KISHORE GHOSH | 194.76 | 0 | 0 | 0
Total | [13 empty] | 250.58 | 28.56 | 11.4