## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Division | DINGAL AND ITS ADJOINING MOUJAS PWSS | SM/12828 | New | Material Requisition To Resource Division |  |  | RTOR000200/2023-2024 | 1410 | 04/05/2023 | 04/05/2023 | Resource Division | 36.06 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | DINGAL AND ITS ADJOINING MOUJAS PWSS | SM/12828 | New | Electrict quotation bill for TW-II of Dingal pwss (Ref Consumar ID-204198617),Application No-2004571068,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra. |  |  | BILL/03553/2023-2024 | BP-2023-24-600 | 07/02/2024 | 07/02/2024 | WBSEDCL | 0.51 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | DINGAL AND ITS ADJOINING MOUJAS PWSS | SM/12828 | New | Electrict quotation bill for TW-I of Dingal pwss (Ref Consumar ID-204199250),Application No-2004571039,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra. |  |  | BILL/03554/2023-2024 | BP-2023-24-599 | 07/02/2024 | 07/02/2024 | WBSEDCL | 6.95 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Debra | Midnapore Division | DINGAL AND ITS ADJOINING MOUJAS PWSS | SM/12828 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with laying distribution system , Sinking of Tube Well , Pump House, Boundary Wall, laying of Rising Main & Providing Functional Household Tap Connection (4740 Nos) including 2 years Operation & Maintenance For Dingal, Duan and Gobindapur Pipe water supply Scheme within Debra Block Under Kharagpur Sub Division of Midnapore Division PHE Dte. Under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division | ORD/000211/2023-2024 | 2826/MD | 07/08/2023 | 30/09/2025 | GOBINDA MAITY | 1375.06 | 0 | 0 | 74
5 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | DINGAL AND ITS ADJOINING MOUJAS PWSS | SM/12828 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DINGAL AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001941/2022-2023 | 826/W/MMD | 24/03/2023 | 31/10/2025 | P.K.ENGINEERING | 22.65 | 0 | 0 | 50
Total | [13 empty] | 1441.24 | 0 | 0