## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Division | BARBHUNA BASAN STAND ALONE PWSS | SM/12841 | New | Material Requisition To Resource Division |  |  | RTOR000174/2023-2024 | 1357/MD | 02/05/2023 | 02/05/2023 | Resource Division | 0.63 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | BARBHUNA BASAN STAND ALONE PWSS | SM/12841 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BARBHUNA BASAN STAND ALONE PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002006/2022-2023 | 879/W/MMD | 27/03/2023 | 23/09/2023 | DEBSANKER BHATTACHARYA | 5.98 | 4.35 | 72.72 | 40
3 | PASCHIM MEDINIPUR | Debra | Midnapore Division | BARBHUNA BASAN STAND ALONE PWSS | SM/12841 | New | Construction & Installation of 10 Cum Capacity PVC Over Head Reservoir works with laying rising main, distribution system, Sinking of Tube well, Pump House & Providing FHTC (102 Nos.) with 1 year O&M for Barbhuna Basan PWSS within Debra block under Kharagpur Sub Division of Midnapore Division PHE Dte. in Paschim Medinipur District. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra) | ORD/000041/2024-2025 | 2256/MD | 23/07/2024 | 01/05/2025 | BLUE BIRD | 44.33 | 0 | 0 | 50
Total | [13 empty] | 50.93 | 4.35 | 8.53