## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Chaipat (Zone-I & II) & its adjoining mouzas. | SM/12875 | New | Electric quotation for TW-I,ZONE-I for chaipat water supply scheme.Ref consumer Id-204087542 |  |  | BILL/02667/2023-2024 | BP-2023-24-262 | 26/09/2023 | 26/09/2023 | WBSEDCL | 4.7 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Chaipat (Zone-I & II) & its adjoining mouzas. | SM/12875 | New | Laying of Rising main pipeline for Chaipat (Zone-II) PWSS under Daspur-II block within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000361/2024-2025 | 3788/MD | 24/12/2024 | 07/02/2025 | ENVIROEXCELSIOR SOLUTIONS PRIVATE LIMITED | 5.32 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Chaipat (Zone-I & II) & its adjoining mouzas. | SM/12875 | New | Laying of Rising main pipeline for Chaipat (Zone-I) PWSS under Daspur-II block within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000360/2024-2025 | 3787/MD | 24/12/2024 | 07/02/2025 | ENVIROEXCELSIOR SOLUTIONS PRIVATE LIMITED | 6.2 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Chaipat (Zone-I & II) & its adjoining mouzas. | SM/12875 | New | Material Requisition To Resource Division |  |  | RTOR000023/2024-2025 | 3341/MD | 25/11/2024 | 25/11/2024 | Resource Division | 25.58 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Chaipat (Zone-I & II) & its adjoining mouzas. | SM/12875 | New | Electrict quotation bill for TW-I of Chaipat(Zone-II)(Nischintapur) pwss ,(Ref Consumar ID-204219008),Application No-2004604095,Application Type-New Connection,Name of ccc-Sonakhali ccc, block-Daspur-II. |  |  | BILL/00600/2024-2025 |  | 24/04/2024 | 24/04/2024 | WBSEDCL | 3.9 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Chaipat (Zone-I & II) & its adjoining mouzas. | SM/12875 | New | Electrict quotation bill for TW-II of CHAIPAT,ZONE-II pwss (Ref Consumar ID-204239049),Application No-2004633954,Application Type-New Connection,Name of ccc-Sonakhali ccc, block-Daspur-II. |  |  | BILL/04394/2023-2024 | BP-2023-24-817 | 13/03/2024 | 13/03/2024 | WBSEDCL | 13.12 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Chaipat (Zone-I & II) & its adjoining mouzas. | SM/12875 | New | Electrict quotation bill for TW-I of chaipat , Zone-II pwss (Ref Consumar ID-204219008),Application No-2004604095,Application Type-New Connection,Name of ccc-Sonakhali ccc, block-Daspur-II. |  |  | BILL/03932/2023-2024 | BP-2023-24-726 | 23/02/2024 | 23/02/2024 | WBSEDCL | 3.9 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Chaipat (Zone-I & II) & its adjoining mouzas. | SM/12875 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 2 nos. 400 cum OHR (Intze type with pile foundation) & 3 Nos. 300 Cum OHR & Accommodate FHTC (10,944 Nos,) under JJM with allied work for (i) Chaipat (Zone-I & Zone-II) & its adjoining mouzas W/S scheme (ii) Kelegoda & its adjoining mouzas W/S Scheme (iii) Uttarbar (Zone-I & Zone-II) & its adjoining mouzas W/S Scheme in Daspur- II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000514/2022-2023 | 2556/MD | 15/12/2022 | 06/05/2026 | M/S. S.S. ENTERPRISE | 2473.34 | 0 | 0 | 18
9 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Chaipat (Zone-I & II) & its adjoining mouzas. | SM/12875 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-04-2025 to 28-09-2025 (Vehicle No. WB06N 8474) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002214/2024-2025 | 432/MMSD-I | 26/03/2025 | 23/09/2025 | S.K.ENTERPRISE | 4.11 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Chaipat (Zone-I & II) & its adjoining mouzas. | SM/12875 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Chaipat (Zone-I & II) & its adjoining mouzas. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001938/2022-2023 | 823/W/MMD | 24/03/2023 | 01/09/2025 | M/S. SAJAHAN CHOWDHURY | 47.51 | 0 | 0 | 80
Total | [13 empty] | 2587.67 | 0 | 0