## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Division | GOPINATHPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12986 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division |  | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 30/01/2023 | JADAVPUR UNIVERSITY | 100.36 | 4.78 | 4.76 | 90
2 | PASCHIM MEDINIPUR | Debra | Midnapore Division | GOPINATHPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12986 | New | Construction of different capacity R.C.C. Over Head Reservoir Pile / Raft Foundation works with Laying rising main, Distribution system, Sinking of Tube well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (1,137 Nos.) including 1 year operation & maintenance for Gopinathpur Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division, PHE Dte. under Paschim Medinipur district. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra) | ORD/000037/2023-2024 | 1340/MD | 28/04/2023 | 29/10/2024 | SUJATA CONSTRUCTION | 367.16 | 166.86 | 45.45 | 45
3 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | GOPINATHPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12986 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for GOPINATHPUR AND IT'S ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000079/2023-2024 | 1277/W/MMD | 04/05/2023 | 31/10/2023 | MENAKA ENTERPRISE | 22.54 | 0 | 0 | 80
4 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | GOPINATHPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12986 | New | Electrict quotation bill for TW-I of Gopinathpur pwss (Ref Consumar ID-204252433),Application No-2004648562,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra. |  |  | BILL/00284/2024-2025 | BP-2024-25-40 | 18/04/2024 | 18/04/2024 | WBSEDCL | 4.27 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | GOPINATHPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12986 | New | Electrict quotation bill for TW-II of Gopinathpur pwss (Ref Consumar ID-204251445),Application No-2004648522,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra. |  |  | BILL/00286/2024-2025 | BP-2024-25-39 | 18/04/2024 | 18/04/2024 | WBSEDCL | 3.81 | 0 | 0 | 0
Total | [13 empty] | 498.15 | 171.64 | 34.46