## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Division | KANAKPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12988 | New | Material Requisition To Resource Division |  |  | RTOR000219/2023-2024 | 1516/MD | 12/05/2023 | 12/05/2023 | Resource Division | 34.57 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | KANAKPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12988 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KANAKPUR AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001594/2022-2023 | 476/W/MMD | 20/03/2023 | 16/09/2023 | M/S. SAJAHAN CHOWDHURY | 23 | 18.08 | 78.61 | 60
Total | [13 empty] | 57.57 | 18.08 | 31.41