## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | ANGUA AND ADJOINING MOUJAS PWSS | SM/12989 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh, Dantan-I & Dantan-II Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (A) Narayangarh block- (1) Kasba, (B) Dantan-I block - (1) Birbhadrapur, (2) Menakapur & (3) Benapura, (C) Dantan-II block - (1) Kusumda (Turkakasba)] | AE/RWS Midnapore Sub Division |  | ORD/000733/2022-2023 | 707/MD | 06/03/2023 | 10/04/2023 | JADAVPUR UNIVERSITY | 23.9 | 0 | 0 | 20
2 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | ANGUA AND ADJOINING MOUJAS PWSS | SM/12989 | New | Material Requisition To Resource Division |  |  | RTOR000066/2023-2024 | 1280/MD | 28/04/2023 | 28/04/2023 | Resource Division | 28.62 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | ANGUA AND ADJOINING MOUJAS PWSS | SM/12989 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of ANGUA PWSS. REF CONSUMER ID-204310356 APPLICATION NO-2004739370 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I |  |  | BILL/01031/2024-2025 | BP-2024-25-211 | 28/05/2024 | 28/05/2024 | WBSEDCL | 4.55 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | ANGUA AND ADJOINING MOUJAS PWSS | SM/12989 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of ANGUA PWSS. REF CONSUMER ID-204310283 APPLICATION NO-2004740900, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I |  |  | BILL/01024/2024-2025 | BP-2024-25-210 | 28/05/2024 | 28/05/2024 | WBSEDCL | 6.04 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | ANGUA AND ADJOINING MOUJAS PWSS | SM/12989 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (72023 Nos.) for 41 Nos. PWSS within DANTAN-I, DANTANII & KESHIARY Block Pipe Water Supply Scheme under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),JE RWS Kharagpur Sub-Division( Keshiary),JE RWS Midnapur Sub-Division( Dantan-I),JE2 Kharagpur Sub Division | ORD/000277/2023-2024 | 5056/MD | 26/10/2023 | 26/03/2026 | ENGINEERING PROJECTS (INDIA) LIMITED | 18003.47 | 0 | 0 | 30
6 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | ANGUA AND ADJOINING MOUJAS PWSS | SM/12989 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for ANGUA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001902/2022-2023 | 801/W/MMD | 24/03/2023 | 30/04/2025 | RSA ENTERPRISE | 21.59 | 0 | 0 | 35
Total | [13 empty] | 18088.18 | 0 | 0