## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | BAMANBIRUA AND ADJOINING MOUJAS PWSS | SM/12991 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division |  | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 30/01/2023 | JADAVPUR UNIVERSITY | 100.36 | 0 | 0 | 90
2 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | BAMANBIRUA AND ADJOINING MOUJAS PWSS | SM/12991 | New | Material Requisition To Resource Division |  |  | RTOR000106/2022-2023 | 217/MD | 16/01/2023 | 16/01/2023 | Resource Division | 14.02 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | BAMANBIRUA AND ADJOINING MOUJAS PWSS | SM/12991 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BAMANBIRUA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Sourav Mondal, JE/Midnapur Mechanical Sub-Division- | ORD/001385/2022-2023 | 2396/W/MMD | 31/12/2022 | 17/06/2025 | M/S EMMESS | 22.89 | 0 | 0 | 20
4 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | BAMANBIRUA AND ADJOINING MOUJAS PWSS | SM/12991 | New | Material Requisition To Resource Division |  |  | RTOR000121/2024-2025 | 3457/MD | 25/11/2024 | 25/11/2024 | Resource Division | 11.03 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | BAMANBIRUA AND ADJOINING MOUJAS PWSS | SM/12991 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of BAMANBIRUAN PWSS. REF CONSUMER ID-204183585, APPLICATION NO-2004552319, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I |  |  | BILL/04059/2023-2024 | BP-2023-24-747 | 27/02/2024 | 27/02/2024 | WBSEDCL | 4.81 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | BAMANBIRUA AND ADJOINING MOUJAS PWSS | SM/12991 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of BAMANBIRUAN PWSS. REF CONSUMER ID-204244321, APPLICATION NO-2004640141, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I |  |  | BILL/02388/2024-2025 | C092403245767 | 04/09/2024 | 04/09/2024 | WBSEDCL | 6.16 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | BAMANBIRUA AND ADJOINING MOUJAS PWSS | SM/12991 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House & laying of rising main, Boundary Wall & Providing Functional Household Tap Connection (18944 Nos) including 2 years Operation & Maintenance for ANTRI, PALASIA, BAMAN BIRUA, BAMANDA, GAZIPUR PATNA, PUNDRA, SALIKOTHA & SARANG Pipe water supply Scheme within Dantan-I Block Under Kharagpur Sub Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I) | ORD/000039/2023-2024 | 1355/MD | 02/05/2023 | 01/06/2026 | SWACH ENVIRONMENT PRIVATE LIMITED | 4465.22 | 0 | 0 | 45
Total | [13 empty] | 4624.48 | 0 | 0