## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | BAMANDA AND ADJOINING MOUJAS PWSS | SM/12993 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division |  | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 30/01/2023 | JADAVPUR UNIVERSITY | 100.36 | 4.78 | 4.76 | 90
2 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | BAMANDA AND ADJOINING MOUJAS PWSS | SM/12993 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh, Dantan-I & Dantan-II Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (A) Narayangarh block- (1) Kasba, (B) Dantan-I block - (1) Birbhadrapur, (2) Menakapur & (3) Benapura, (C) Dantan-II block - (1) Kusumda (Turkakasba)] | AE/RWS Midnapore Sub Division |  | ORD/000733/2022-2023 | 707/MD | 06/03/2023 | 10/04/2023 | JADAVPUR UNIVERSITY | 23.9 | 0 | 0 | 20
3 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | BAMANDA AND ADJOINING MOUJAS PWSS | SM/12993 | New | Material Requisition To Resource Division |  |  | RTOR000083/2022-2023 | 192/MD | 16/01/2023 | 16/01/2023 | Resource Division | 17.1 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | BAMANDA AND ADJOINING MOUJAS PWSS | SM/12993 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BAMANDA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001606/2022-2023 | 486/W/MMD | 20/03/2023 | 31/12/2024 | DIPALI CONSTRUCTION | 22.98 | 10.62 | 46.23 | 20
5 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | BAMANDA AND ADJOINING MOUJAS PWSS | SM/12993 | New | Material Requisition To Resource Division |  |  | RTOR000122/2024-2025 | 3458/MD | 25/11/2024 | 25/11/2024 | Resource Division | 14.16 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | BAMANDA AND ADJOINING MOUJAS PWSS | SM/12993 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of BAMANDA PWSS. REF CONSUMER ID-204212537, APPLICATION NO-2004593868, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I |  |  | BILL/03739/2023-2024 | BP-2023-24-691 | 16/02/2024 | 16/02/2024 | WBSEDCL | 4.5 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | BAMANDA AND ADJOINING MOUJAS PWSS | SM/12993 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of BAMANDA PWSS. REF CONSUMER ID-204302072, APPLICATION NO-2004723744, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I |  |  | BILL/01023/2024-2025 | BP-2024-25-212 | 28/05/2024 | 28/05/2024 | WBSEDCL | 2.35 | 0 | 0 | 0
Total | [13 empty] | 185.34 | 15.4 | 8.31