## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-I | Midnapore Division | BARAMURA AND ADJOINING MOUJAS PWSS | SM/12994 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (1,23,486 Nos.) for 89 Nos. PWSS within GARBETA-I, GARBETA-III, SALBANI & GARBETA-II Block Pipe Water Supply Scheme under Midnapore Sadar Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II),JE RWS Sadar Sub-Division(Garbeta-III),JE1 Sadar Sub-division,JE2 Sadar Sub-division | ORD/000282/2023-2024 | 5091/MD | 30/10/2023 | 19/10/2026 | RMN INFRASTRUCTURES LIMITED | 34739.93 | 142.34 | 0.41 | 40
2 | PASCHIM MEDINIPUR | Garbeta-I | Midnapore Division | BARAMURA AND ADJOINING MOUJAS PWSS | SM/12994 | New | Material Requisition To Resource Division |  |  | RTOR000043/2023-2024 | 1184/MD | 26/04/2023 | 26/04/2023 | Resource Division | 22.88 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Garbeta-I | Central Drilling | BARAMURA AND ADJOINING MOUJAS PWSS | SM/12994 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). |  |  | ORD/000002/2024-2025 | 188/CDD | 17/05/2024 | 17/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 700.39 | 9.65 | 1.38 | 15
4 | PASCHIM MEDINIPUR | Garbeta-I | Central Drilling | BARAMURA AND ADJOINING MOUJAS PWSS | SM/12994 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 23/10/2024 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 9.5 | 2.07 | 10
5 | PASCHIM MEDINIPUR | Garbeta-I | Jhargram Mechanical Division | BARAMURA AND ADJOINING MOUJAS PWSS | SM/12994 | New | NEW SERVICE CONNECTION CHARGES AT BARAMURA T/W-I |  |  | BILL/00916/2025-2026 |  | 22/08/2025 | 22/08/2025 | WBSEDCL | 3.91 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Garbeta-I | Jhargram Mechanical Division | BARAMURA AND ADJOINING MOUJAS PWSS | SM/12994 | New | new service connection charges at Baramura-II |  |  | BILL/01444/2025-2026 |  | 03/11/2025 | 03/11/2025 | WBSEDCL | 4.05 | 0 | 0 | 0
Total | [13 empty] | 35929.85 | 161.49 | 0.45