## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | RADHABALLABHPUR PIPED WATER SUPPLY SCHEME | SM/12997 | New | Material Requisition To Resource Division |  |  | RTOR000040/2022-2023 | 99/MD | 10/01/2023 | 10/01/2023 | Resource Division | 28.38 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | RADHABALLABHPUR PIPED WATER SUPPLY SCHEME | SM/12997 | New | Additional quatation for service connection charge for effecting NSC at Radhaballavpur PWSS vide Application 2004305845. |  |  | BILL/01864/2023-2024 | BP-2023-24-234 | 07/09/2023 | 07/09/2023 | WBSEDCL | 1.91 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | RADHABALLABHPUR PIPED WATER SUPPLY SCHEME | SM/12997 | New | Electric quotation bill for new connection at Tw-I of Radhaballabhpur water supply scheme. Consumer ID-204030193. |  |  | BILL/00580/2023-2024 | BP-2023-24-127 | 13/07/2023 | 13/07/2023 | WBSEDCL | 0.28 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | RADHABALLABHPUR PIPED WATER SUPPLY SCHEME | SM/12997 | New | Electric quotation bill for new connection at Tw No-II of Radhaballabhpur water supply scheme. Consumer ID-204018509. |  |  | BILL/00582/2023-2024 | BP-2023-24-126 | 13/07/2023 | 13/07/2023 | WBSEDCL | 0.28 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | RADHABALLABHPUR PIPED WATER SUPPLY SCHEME | SM/12997 | New | Additional quotation for service connection charge for effecting NSC vide Application No-2004305839. |  |  | BILL/01865/2023-2024 | BP-2023-24-233 | 07/09/2023 | 07/09/2023 | WBSEDCL | 2.14 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | RADHABALLABHPUR PIPED WATER SUPPLY SCHEME | SM/12997 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RADHABALLABHPUR PIPED WATER SUPPLY SCHEME under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001950/2022-2023 | 833/W/MMD | 24/03/2023 | 20/09/2023 | ORIENTAL ENGINEERING CO. | 23.76 | 22.12 | 93.13 | 50
7 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | RADHABALLABHPUR PIPED WATER SUPPLY SCHEME | SM/12997 | New | Laying Rising main from 2nd tube well to 1st tube well to OHR for Radhaballavpur & its adjoining mouzas W/S Scheme within Keshpur block under Midnapore Division, PHE Dte. (Length of pipe line = 360.00 Mtr.) | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000761/2023-2024 | 374/MD | 12/02/2024 | 13/03/2024 | MAMPI ENTERPRISE | 9.73 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | RADHABALLABHPUR PIPED WATER SUPPLY SCHEME | SM/12997 | New | Material Requisition To Resource Division |  |  | RTOR000063/2024-2025 | 3383/MD | 25/11/2024 | 25/11/2024 | Resource Division | 14.62 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | RADHABALLABHPUR PIPED WATER SUPPLY SCHEME | SM/12997 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 400 cum OHR (Intze type with Pile foundation) & Accommodate FHTC (2374 Nos.) under JJM with allied work for Radhaballavpur & its adjoining mouzas W/S scheme in Keshpur Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000641/2022-2023 | 578/MD | 23/02/2023 | 17/10/2025 | DULAL CHANDRA DAS | 647.61 | 387.52 | 59.84 | 4
10 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | RADHABALLABHPUR PIPED WATER SUPPLY SCHEME | SM/12997 | New | Supply and delivery LED Smart Bright street light fixture and other related works at P H of Radhaballavpur and other water supply scheme under Midnapur Mechanical Division , P.H.E.Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000062/2025-2026 | 660/MMSD-I | 13/05/2025 | 23/05/2025 | ASHUTOSH DAS & CO. | 1.62 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | RADHABALLABHPUR PIPED WATER SUPPLY SCHEME | SM/12997 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different ongoing piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.- w.e.f.-01-07-2025 to 28-02-2026 (Vehicle No. WB33C 6546) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000513/2025-2026 | 842/MMSD-I | 11/06/2025 | 09/02/2026 | M/S BIKASH DE | 3.66 | 0 | 0 | 0
Total | [13 empty] | 733.99 | 409.65 | 55.81