## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | BHETIAMLA AND ADJOINING MOUJAS PWSS | SM/12998 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BHETIAMLA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Sourav Mondal, JE/Midnapur Mechanical Sub-Division- | ORD/001604/2022-2023 | 485/W/MMD | 20/03/2023 | 16/09/2023 | DIAMOND ELECTRICAL WORKS | 22.95 | 0 | 0 | 10
2 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | BHETIAMLA AND ADJOINING MOUJAS PWSS | SM/12998 | New | Material Requisition To Resource Division |  |  | RTOR000069/2023-2024 | 1277/MD | 28/04/2023 | 28/04/2023 | Resource Division | 27.29 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | BHETIAMLA AND ADJOINING MOUJAS PWSS | SM/12998 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of BHETIA MALA PWSS. REF CONSUMER ID-204310299 APPLICATION NO-2004739419, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I |  |  | BILL/01030/2024-2025 | BP-2024-25-209 | 28/05/2024 | 28/05/2024 | WBSEDCL | 6.22 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | BHETIAMLA AND ADJOINING MOUJAS PWSS | SM/12998 | New | Joint inspection regarding laying of water supply pipe line of under ground Railway track crossing of 600mm dia M.S. carrier pipe by jack pushing method by PHE at Km 171/06/08-171/05-07 between DNT-AGV under the jurisdiction of ADEN/South/KGP. [Application ID - SER-KGP-2024-WL-181] |  |  | BILL/00806/2024-2025 | BP-2024-25-444 | 07/10/2024 | 07/10/2024 | SOUTH EASTERN RAILWAY | 6.32 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | BHETIAMLA AND ADJOINING MOUJAS PWSS | SM/12998 | New | Joint inspection regarding laying of water supply pipe line of under ground Railway track crossing of 600mm dia M.S. carrier pipe by jack pushing method by PHE at Km 171/06/08-171/05-07 between DNT-AGV under the jurisdiction of ADEN/South/KGP. [Application ID - SER-KGP-2024-WL-182] |  |  | BILL/00808/2024-2025 | BP-2024-25-444 | 07/10/2024 | 07/10/2024 | SOUTH EASTERN RAILWAY | 5.93 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | BHETIAMLA AND ADJOINING MOUJAS PWSS | SM/12998 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of BHETIA MALA PWSS. REF CONSUMER ID-204310335, APPLICATION NO-2004739400, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I |  |  | BILL/01029/2024-2025 | BP-2024-25-208 | 28/05/2024 | 28/05/2024 | WBSEDCL | 5.73 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | BHETIAMLA AND ADJOINING MOUJAS PWSS | SM/12998 | New | Joint inspection regarding laying of water supply pipe line of under ground Railway track crossing of 600mm dia M.S. carrier pipe by jack pushing method by PHE at Km 171/06/08-171/05-07 between DNT-AGV under the jurisdiction of ADEN/South/KGP. [Application ID - SER-KGP-2024-WL-182] |  |  | BILL/00807/2024-2025 | BP-2024-25-444 | 07/10/2024 | 07/10/2024 | SOUTH EASTERN RAILWAY | 6.24 | 0 | 0 | 0
Total | [13 empty] | 80.68 | 0 | 0