## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | DAKSHIN AMRIA AND ADJOINING MOUJAS PWSS | SM/12999 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DAKSHIN AMRIA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Sourav Mondal, JE/Midnapur Mechanical Sub-Division- | ORD/001758/2022-2023 | 648/W/MMD | 20/03/2023 | 16/09/2023 | MANIK CHANDRA SAHA | 21.56 | 16.28 | 75.49 | 25
2 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | DAKSHIN AMRIA AND ADJOINING MOUJAS PWSS | SM/12999 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (72023 Nos.) for 41 Nos. PWSS within DANTAN-I, DANTANII & KESHIARY Block Pipe Water Supply Scheme under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),JE RWS Kharagpur Sub-Division( Keshiary),JE RWS Midnapur Sub-Division( Dantan-I),JE2 Kharagpur Sub Division | ORD/000277/2023-2024 | 5056/MD | 26/10/2023 | 30/06/2026 | ENGINEERING PROJECTS (INDIA) LIMITED | 18003.47 | 56.4 | 0.31 | 30
3 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | DAKSHIN AMRIA AND ADJOINING MOUJAS PWSS | SM/12999 | New | Material Requisition To Resource Division |  |  | RTOR000062/2023-2024 | 1283/MD | 28/04/2023 | 28/04/2023 | Resource Division | 29.58 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | DAKSHIN AMRIA AND ADJOINING MOUJAS PWSS | SM/12999 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF DAKSHIN AMRIA PWSS. REF CONSUMER ID-204389348, APPLICATION NO-2004882536, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I |  |  | BILL/02411/2024-2025 | C092442004530 | 27/09/2024 | 27/09/2024 | WBSEDCL | 9.74 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | DAKSHIN AMRIA AND ADJOINING MOUJAS PWSS | SM/12999 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of DAKSHIN AMRIA PWSS. REF CONSUMER ID-204310379 APPLICATION NO-2004739365 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I |  |  | BILL/01026/2024-2025 | BP-2024-25-205 | 28/05/2024 | 28/05/2024 | WBSEDCL | 3.79 | 0 | 0 | 0
Total | [13 empty] | 18068.15 | 72.68 | 0.4