## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-I | Midnapore Division | DHENGADAHA AND ADJOINING MOUJAS PWSS | SM/13000 | New | Material Requisition To Resource Division |  |  | RTOR000038/2023-2024 | 1180/MD | 26/04/2023 | 26/04/2023 | Resource Division | 28.14 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Garbeta-I | Jhargram Mechanical Division | DHENGADAHA AND ADJOINING MOUJAS PWSS | SM/13000 | New | NEW SERVICE CONNECTION CHARGES AT DHENGADAHA TW-II WATER SUPPLY SCHEME |  |  | BILL/00572/2024-2025 | 251/JMD | 10/07/2024 | 10/07/2024 | WBSEDCL | 5.83 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Garbeta-I | Jhargram Mechanical Division | DHENGADAHA AND ADJOINING MOUJAS PWSS | SM/13000 | New | NEW SERVICE CONNECTION CHARGES AT DHENGADAHA TW-I WATER SUPPLY SCHEME |  |  | BILL/00571/2024-2025 | 250/JMD | 10/07/2024 | 10/07/2024 | WBSEDCL | 5.32 | 0 | 0 | 0
Total | [13 empty] | 39.29 | 0 | 0