## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Salbani | Central Drilling | KARNAGAR AND ADJOINING MAOUJAS PWSS | SM/13001 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 13.42 | 0.06 | 11
2 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | KARNAGAR AND ADJOINING MAOUJAS PWSS | SM/13001 | New | Laying distribution pipe line & Accommodate FHTC (250 Nos.) under JJM with allied work for Karnagar PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000104/2023-2024 | 2486/MD | 17/07/2023 | 30/07/2026 | GOUTAM RAY | 47.26 | 30.65 | 64.85 | 70
3 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | KARNAGAR AND ADJOINING MAOUJAS PWSS | SM/13001 | New | Sinking of Two nos. 250 X 150 mm dia. X 160 mtr. depth deep tube well by direct rotary method under JJM with allied work for Karnagar PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000111/2023-2024 | 2512/MD | 18/07/2023 | 08/08/2023 | FIROJ KHAN | 16.16 | 15.22 | 94.22 | 100
4 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | KARNAGAR AND ADJOINING MAOUJAS PWSS | SM/13001 | New | Laying Rising main, Laying distribution pipe line, & Accommodate FHTC (450 Nos.) including 2 years O & M under JJM with allied work for Karnagar PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-D] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000269/2023-2024 | 3243/MD | 11/09/2023 | 10/11/2023 | ASHIM KUMAR DEY | 185.94 | 7.89 | 4.24 | 10
5 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | KARNAGAR AND ADJOINING MAOUJAS PWSS | SM/13001 | New | Laying distribution pipe line & Accommodate FHTC (250 Nos.) under JJM with allied work for Karnagar PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000242/2023-2024 | 3097/MD | 25/08/2023 | 24/10/2023 | PULLOCK KUMAR GHOSH | 46.42 | 29.3 | 63.11 | 10
6 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | KARNAGAR AND ADJOINING MAOUJAS PWSS | SM/13001 | New | Construction Pump House, Boundary wall & Accommodate FHTC (350 Nos.) under JJM with allied work for Karnagar PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-E] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000268/2023-2024 | 3242/MD | 11/09/2023 | 28/08/2026 | MIDNAPUR PIPE CONCERN | 53.54 | 14.63 | 27.32 | 51
7 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | KARNAGAR AND ADJOINING MAOUJAS PWSS | SM/13001 | New | Material Requisition To Resource Division |  |  | RTOR000179/2023-2024 | 1358/MD | 02/05/2023 | 02/05/2023 | Resource Division | 29.51 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | KARNAGAR AND ADJOINING MAOUJAS PWSS | SM/13001 | New | Construction of 250 CuM OHR (Intez type with solid raft) & Accommodate FHTC (435 Nos.) under JJM with allied work for Karnagar PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-F] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000176/2024-2025 | 3159/MD | 04/10/2024 | 28/03/2026 | D M CONSTRUCTION | 107.46 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | KARNAGAR AND ADJOINING MAOUJAS PWSS | SM/13001 | New | New service connection charges for Karnagarg, tw-I w/s scheme |  |  | BILL/01305/2023-2024 | 76/JMD | 12/02/2024 | 12/02/2024 | WBSEDCL | 3.23 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | KARNAGAR AND ADJOINING MAOUJAS PWSS | SM/13001 | New | New service connection charges for Karnagarh, tw-II w/s scheme |  |  | BILL/01306/2023-2024 | 77/JMD | 14/02/2024 | 14/02/2024 | WBSEDCL | 2.99 | 0 | 0 | 0
Total | [13 empty] | 21832.28 | 111.11 | 0.51