## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | BARAKEUNDI AND ADJOINING MOUJAS PWSS | SM/13002 | New | Material Requisition To Resource Division |  |  | RTOR000134/2023-2024 | 1257/MD | 28/04/2023 | 28/04/2023 | Resource Division | 25.04 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | BARAKEUNDI AND ADJOINING MOUJAS PWSS | SM/13002 | New | New service connection charges for Barakeundi w/s scheme, t/w no.II |  |  | BILL/01374/2023-2024 | 37/JMD | 11/03/2024 | 11/03/2024 | WBSEDCL | 3.45 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | BARAKEUNDI AND ADJOINING MOUJAS PWSS | SM/13002 | New | New service connection charges for Barakeundi w/s scheme, t/w no.I |  |  | BILL/01373/2023-2024 | 36/JMD | 11/03/2024 | 11/03/2024 | WBSEDCL | 3.51 | 0 | 0 | 0
Total | [13 empty] | 31.99 | 0 | 0