## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | BHANSRA AND ADJOINING MOUJAS PWSS | SM/13005 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Keshiary Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (1) Bhansra (JL.- 138, Plot-455/738), (2) Gaganeshwar (JL.- 154, Plot- 454), (3) Haripura (JL.- 130, Plot-13), (4) Panchyar (JL.- 194, Plot-400), (5) Santrapur (JL.- 57, Plot-218)] | AE Kharagpur Sub-division |  | ORD/000651/2022-2023 | 746/MD | 13/03/2023 | 12/04/2023 | JADAVPUR UNIVERSITY | 23.9 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | BHANSRA AND ADJOINING MOUJAS PWSS | SM/13005 | New | Material Requisition To Resource Division |  |  | RTOR000118/2023-2024 | 1309/MD | 28/04/2023 | 28/04/2023 | Resource Division | 33.81 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | BHANSRA AND ADJOINING MOUJAS PWSS | SM/13005 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BHANSRA AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000162/2023-2024 | 1404/W/MMD | 02/06/2023 | 22/05/2025 | DEBJYOTI BASU | 22.78 | 0 | 0 | 20
4 | PASCHIM MEDINIPUR | Keshiary | Central Drilling | BHANSRA AND ADJOINING MOUJAS PWSS | SM/13005 | New | Providing drilling crew and other allied works for construction of Tube Well ( 250mm X150mm X 220 Mtrs. Depth) by utilising Departmental Machineries for BHANSRA W/S Scheme (T/W-I & II) , Keshiery Block under Paschim Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000088/2023-2024 | 389/CDD | 18/05/2023 | 10/07/2024 | PADMA ENGINEERING & CO. | 25.43 | 0 | 0 | 50
5 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | BHANSRA AND ADJOINING MOUJAS PWSS | SM/13005 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF BHANSRA PWSS. REF CONSUMER ID-204370484, APPLICATION NO-2004846729, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY |  |  | BILL/02125/2024-2025 | C082448282150 | 02/09/2024 | 02/09/2024 | WBSEDCL | 3.62 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | BHANSRA AND ADJOINING MOUJAS PWSS | SM/13005 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (72023 Nos.) for 41 Nos. PWSS within DANTAN-I, DANTANII & KESHIARY Block Pipe Water Supply Scheme under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),JE RWS Kharagpur Sub-Division( Keshiary),JE RWS Midnapur Sub-Division( Dantan-I),JE2 Kharagpur Sub Division | ORD/000277/2023-2024 | 5056/MD | 26/10/2023 | 26/03/2026 | ENGINEERING PROJECTS (INDIA) LIMITED | 18003.47 | 0 | 0 | 30
Total | [13 empty] | 18113 | 0 | 0