## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-III | Midnapore Division | DAMODARPUR AND ADJOINING MOUJAS PWSS | SM/13008 | New | Material Requisition To Resource Division |  |  | RTOR000057/2023-2024 | 1201/MD | 26/04/2023 | 26/04/2023 | Resource Division | 26.92 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Garbeta-III | Central Drilling | DAMODARPUR AND ADJOINING MOUJAS PWSS | SM/13008 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3 | PASCHIM MEDINIPUR | Garbeta-III | Jhargram Mechanical Division | DAMODARPUR AND ADJOINING MOUJAS PWSS | SM/13008 | New | Supply, delivery & fitting fixing of wooden board & Porcelain fuse unit for receiving power from WBSEDCL at Damodarpur & adjacent water supply schemes of Garhbeta-III block under JJM progamme under Jhargram Mechanical Division, P.H.E Dte. in the district of Paschim Medinipur. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 3784/JMD | 12/07/2024 | 11/08/2024 | MONORANJAN DEY | 2.83 | 0 | 0 | 30
Total | [13 empty] | 21369.51 | 0 | 0