## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Division | KHANAMOHAN AND IT'S ADJOINING MOUJAS PWSS | SM/13024 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division |  | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 30/01/2023 | JADAVPUR UNIVERSITY | 100.36 | 0 | 0 | 90
2 | PASCHIM MEDINIPUR | Debra | Midnapore Division | KHANAMOHAN AND IT'S ADJOINING MOUJAS PWSS | SM/13024 | New | Material Requisition To Resource Division |  |  | RTOR000010/2023-2024 | 1147/MD | 25/04/2023 | 25/04/2023 | Resource Division | 14.87 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | KHANAMOHAN AND IT'S ADJOINING MOUJAS PWSS | SM/13024 | New | Electric qutation bill for khanamohan water supply scheme at pump house NO-I |  |  | BILL/02921/2023-2024 | BP-2023-24-341 | 10/11/2023 | 10/11/2023 | WBSEDCL | 3.06 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | KHANAMOHAN AND IT'S ADJOINING MOUJAS PWSS | SM/13024 | New | Electric quotation bill for khanamohan water supply scheme at pump house N0-II |  |  | BILL/02922/2023-2024 | BP-2023-24-340 | 10/11/2023 | 10/11/2023 | WBSEDCL | 3.61 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Debra | Midnapore Division | KHANAMOHAN AND IT'S ADJOINING MOUJAS PWSS | SM/13024 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works with laying rising main, distribution system , Sinking of Tube Well , Pump House , Boundary Wall, & Providing Functional Household Tap Connection (6348 Nos) including 2 years operation & maintenance For Chak Sulpan, Katai, Khanamohan, Khamra and Kumarsanda Pipe water supply Scheme within Debra Block Under Kharagpur Sub Division of Midnapore Division PHE Dte. Under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE1 Kharagpur Sub-division | ORD/000064/2023-2024 | 2145/MD | 08/06/2023 | 01/10/2025 | GOBINDA MAITY | 1960.6 | 0 | 0 | 65
6 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | KHANAMOHAN AND IT'S ADJOINING MOUJAS PWSS | SM/13024 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KHANAMOHAN AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001898/2022-2023 | 797/W/MMD | 24/03/2023 | 31/07/2025 | BHABANI PRASAD MANNA | 21.62 | 0 | 0 | 80
Total | [13 empty] | 2104.12 | 0 | 0