## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Division | Khamra PWSS, Block-Debra, Dist-Paschim Medinipur | SM/13026 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division |  | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 30/01/2023 | JADAVPUR UNIVERSITY | 100.36 | 4.78 | 4.76 | 90
2 | PASCHIM MEDINIPUR | Debra | Midnapore Division | Khamra PWSS, Block-Debra, Dist-Paschim Medinipur | SM/13026 | New | Material Requisition To Resource Division |  |  | RTOR000012/2023-2024 | 1145/MD | 25/04/2023 | 25/04/2023 | Resource Division | 22.96 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | Khamra PWSS, Block-Debra, Dist-Paschim Medinipur | SM/13026 | New | Electric quotation bill for khamra pwss at TW-I (Ref Id-204169703) |  |  | BILL/03243/2023-2024 | BP-2023-24-490 | 29/12/2023 | 29/12/2023 | WBSEDCL | 6.37 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | Khamra PWSS, Block-Debra, Dist-Paschim Medinipur | SM/13026 | New | lectrict quotation bill for TW-II of KHAMRA pwss (Ref Consumar ID-204235950),Application No-2004627275,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra |  |  | BILL/04395/2023-2024 | BP-2023-24-814 | 13/03/2024 | 13/03/2024 | WBSEDCL | 3.17 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Debra | Midnapore Division | Khamra PWSS, Block-Debra, Dist-Paschim Medinipur | SM/13026 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works with laying rising main, distribution system , Sinking of Tube Well , Pump House , Boundary Wall, & Providing Functional Household Tap Connection (6348 Nos) including 2 years operation & maintenance For Chak Sulpan, Katai, Khanamohan, Khamra and Kumarsanda Pipe water supply Scheme within Debra Block Under Kharagpur Sub Division of Midnapore Division PHE Dte. Under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE1 Kharagpur Sub-division | ORD/000064/2023-2024 | 2145/MD | 08/06/2023 | 01/10/2025 | GOBINDA MAITY | 1960.6 | 318.74 | 16.26 | 65
6 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | Khamra PWSS, Block-Debra, Dist-Paschim Medinipur | SM/13026 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Khamra PWSS, Block-Debra, Dist-Paschim Medinipur under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001294/2022-2023 | 2297/W/MMD | 29/12/2022 | 30/06/2025 | ABHIJIT BASU | 22.87 | 12.1 | 52.9 | 45
Total | [13 empty] | 2116.33 | 335.61 | 15.86