## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | MALIGHATI AND ITS ADJOINING MOUJAS PWSS | SM/13027 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for MALIGHATI AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001376/2022-2023 | 2387/W/MMD | 31/12/2022 | 29/06/2023 | BALAJI CONSTRUCTION | 22.89 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Debra | Midnapore Division | MALIGHATI AND ITS ADJOINING MOUJAS PWSS | SM/13027 | New | Sinking of Tube Well, Laying of Rising Main, Laying distribution pipe line, Pump House, 300 cum OHR (Intze type with solid raft) & Accommodate FHTC (1,763 Nos.) including 2 years operation & maintenance under JJM with allied work for Malighati & its adjoining mouzas W/S Scheme in Debra Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra) | ORD/000247/2023-2024 | 3054/MD | 23/08/2023 | 21/01/2027 | DIAMOND ENGINEERS CO-OPERATIVE SOCIETY LTD. | 448.29 | 137.79 | 30.74 | 40
3 | PASCHIM MEDINIPUR | Debra | Midnapore Division | MALIGHATI AND ITS ADJOINING MOUJAS PWSS | SM/13027 | New | Material Requisition To Resource Division |  |  | RTOR000225/2023-2024 | 1509/MD | 12/05/2023 | 12/05/2023 | Resource Division | 26.87 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | MALIGHATI AND ITS ADJOINING MOUJAS PWSS | SM/13027 | New | Electrict quotation bill for TW-II of Malighati pwss (Ref Consumar ID-204391665),Application No-2004886446,Application Type-New Connection,Name of ccc-Lowada ccc, block-debra |  |  | BILL/02422/2024-2025 | C092443140214 | 27/09/2024 | 27/09/2024 | WBSEDCL | 3.8 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | MALIGHATI AND ITS ADJOINING MOUJAS PWSS | SM/13027 | New | Electrict quotation bill for TW-I of Malighati (Ref Consumar ID-204391662),Application No-2004886364, Application Type-New Connection,Name of ccc-Lowada ccc, block-debra |  |  | BILL/02423/2024-2025 | C092443138989 | 27/09/2024 | 27/09/2024 | WBSEDCL | 1.19 | 0 | 0 | 0
Total | [13 empty] | 503.03 | 137.79 | 27.39