## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-I | Midnapore Division | PATHARISOL AND ADJOINING MOUJAS PWSS | SM/13030 | New | Material Requisition To Resource Division |  |  | RTOR000037/2023-2024 | 1179/MD | 26/04/2023 | 26/04/2023 | Resource Division | 28.94 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Garbeta-I | Jhargram Mechanical Division | PATHARISOL AND ADJOINING MOUJAS PWSS | SM/13030 | New | NEW SERVICE CONNECTION CHARGES AT PATHRISOLE TW-I WATER SUPPLY SCHEME |  |  | BILL/00565/2024-2025 | 244/JMD | 10/07/2024 | 10/07/2024 | WBSEDCL | 7.8 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Garbeta-I | Jhargram Mechanical Division | PATHARISOL AND ADJOINING MOUJAS PWSS | SM/13030 | New | NEW SERVICE CONNECTION CHARGES AT PATHRISOLE TW-II WATER SUPPLY SCHEME |  |  | BILL/00566/2024-2025 | 245/JMD | 10/07/2024 | 10/07/2024 | WBSEDCL | 3.93 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Garbeta-I | Central Drilling | PATHARISOL AND ADJOINING MOUJAS PWSS | SM/13030 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | PASCHIM MEDINIPUR | Garbeta-I | Midnapore Division | PATHARISOL AND ADJOINING MOUJAS PWSS | SM/13030 | New | Route survey & way leave permission along & across of National Highway in Patharisol PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000192/2025-2026 | 1628/MD | 06/08/2025 | 27/08/2025 | PIONEER SURVEYORS | 9.55 | 0 | 0 | 0
Total | [13 empty] | 21389.98 | 0 | 0