## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | PATNA PWSS, BLOCK - DEBRA, PASCHIM MEDINIPUR | SM/13031 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Patna PWSS, BLOCK - DEBRA Dist-Paschim Medinipur under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001302/2022-2023 | 2304/W/MMD | 29/12/2022 | 25/06/2026 | DEBJYOTI BASU | 22.87 | 14.31 | 62.58 | 50
2 | PASCHIM MEDINIPUR | Debra | Midnapore Division | PATNA PWSS, BLOCK - DEBRA, PASCHIM MEDINIPUR | SM/13031 | New | Construction of 150 Cum, 200 Cum & 250 Cum Capacity R.C.C Over Head Reservoir Over (Intze type with solid raft) works with Laying of Rising Main, Distribution system, Sinking of Tube Well, Pump House & Providing Functional Household Tap Connection (5061 Nos.) including 2 years Operation & Maintenance for Loyada, Madhabpur, Patna and Radhamohanpur-II Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division | ORD/000208/2023-2024 | 2824/MD | 07/08/2023 | 30/07/2025 | MADE AND TRADE CO. | 1346.28 | 290.05 | 21.54 | 75
3 | PASCHIM MEDINIPUR | Debra | Midnapore Division | PATNA PWSS, BLOCK - DEBRA, PASCHIM MEDINIPUR | SM/13031 | New | Material Requisition To Resource Division |  |  | RTOR000221/2023-2024 | 1517/MD | 12/05/2023 | 12/05/2023 | Resource Division | 11.96 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | PATNA PWSS, BLOCK - DEBRA, PASCHIM MEDINIPUR | SM/13031 | New | Electrict quotation bill for TW-I of Patna pwss (Ref Consumar ID-204251327),Application No-2004648431,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra. |  |  | BILL/00285/2024-2025 | BP-2024-25-42 | 18/04/2024 | 18/04/2024 | WBSEDCL | 3.6 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | PATNA PWSS, BLOCK - DEBRA, PASCHIM MEDINIPUR | SM/13031 | New | Electrict quotation bill for TW-II of Patna pwss (Ref Consumar ID-204252309),Application No-2004648500,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra. |  |  | BILL/00287/2024-2025 | BP-2024-25-41 | 18/04/2024 | 18/04/2024 | WBSEDCL | 5.21 | 0 | 0 | 0
Total | [13 empty] | 1389.92 | 304.37 | 21.9