## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | PIPED WATER SUPPLY SCHEME FOR RANIAR AND IT'S ADJOINING MOUZAS | SM/13032 | New | Material Requisition To Resource Division |  |  | RTOR000036/2022-2023 | 97/MD | 10/01/2023 | 10/01/2023 | Resource Division | 15.44 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR RANIAR AND IT'S ADJOINING MOUZAS | SM/13032 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PIPED WATER SUPPLY SCHEME FOR RANIAR AND IT'S ADJOINING MOUZASunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001432/2023-2024 | 3086/W/MMD | 29/11/2023 | 28/02/2025 | M/S BARMAN ROY TRADERS | 25.52 | 0 | 0 | 20
3 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | PIPED WATER SUPPLY SCHEME FOR RANIAR AND IT'S ADJOINING MOUZAS | SM/13032 | New | Material Requisition To Resource Division |  |  | RTOR000059/2024-2025 | 3379/MD | 25/11/2024 | 25/11/2024 | Resource Division | 16.42 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR RANIAR AND IT'S ADJOINING MOUZAS | SM/13032 | New | Electric quotation bill for Tw No-II of RANIOR PWSS.(Ref Consumer ID-204200319), APPLICATION NO-2004571260, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC- UPPERKUAI CCC, BLOCK-KESHPUR |  |  | BILL/03551/2023-2024 | BP-2023-24-615 | 07/02/2024 | 07/02/2024 | WBSEDCL | 4.85 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | PIPED WATER SUPPLY SCHEME FOR RANIAR AND IT'S ADJOINING MOUZAS | SM/13032 | New | Electric quotation bill for Tw No-I of RANIOR PWSS.(Ref Consumer ID-204200356), APPLICATION NO-2004571235, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC- UPPERKUAI CCC. |  |  | BILL/03549/2023-2024 | BP-2023-24-614 | 07/02/2024 | 07/02/2024 | WBSEDCL | 4.15 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | PIPED WATER SUPPLY SCHEME FOR RANIAR AND IT'S ADJOINING MOUZAS | SM/13032 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 400 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2725 nos) under JJM with allied work for Raniar PWSS in Keshpur Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000069/2023-2024 | 2420/MD | 13/07/2023 | 29/10/2025 | BANERJEE CONSTRUCTION | 800.44 | 0 | 0 | 66
7 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | PIPED WATER SUPPLY SCHEME FOR RANIAR AND IT'S ADJOINING MOUZAS | SM/13032 | New | Laying of rising main & interconnection for Raniar & its adjoining mouzas PWSS, Block: - Keshpur, District: - Paschim Midnapore under Midnapore Division, PHE Dte. (Length = 730 Mtr.) | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000436/2024-2025 | 321/MD | 29/01/2025 | 15/03/2025 | ASHOK BANERJEE | 6.81 | 0 | 0 | 0
Total | [13 empty] | 873.62 | 0 | 0