## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Division | PUNYA AND IT'S ADJOINING MOUJAS PWSS | SM/13033 | New | Material Requisition To Resource Division |  |  | RTOR000093/2023-2024 | 1290/MD | 28/04/2023 | 28/04/2023 | Resource Division | 20.99 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Mechanical | PUNYA AND IT'S ADJOINING MOUJAS PWSS | SM/13033 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF PUNYA PWSS. REF CONSUMER ID-204412273, APPLICATION NO-2004920306, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II |  |  | BILL/02971/2024-2025 | C102455560774 | 30/10/2024 | 30/10/2024 | WBSEDCL | 8.8 | 0 | 0 | 0
Total | [13 empty] | 29.79 | 0 | 0