## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Division | RADHA KANTAPUR AND IT'S ADJOINING MOUJAS | SM/13034 | New | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Radhakantapur & its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. [Name of Proposed PWSS Kalara & its adjoining Mouzas PWSS instead of Radhakantapur & its adjoining Mouzas PWSS] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000105/2022-2023 | 1055/MD | 02/06/2022 | 22/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 6.43 | 6.43 | 100 | 100
2 | PASCHIM MEDINIPUR | Debra | Midnapore Division | RADHA KANTAPUR AND IT'S ADJOINING MOUJAS | SM/13034 | New | Material Requisition To Resource Division |  |  | RTOR000042/2023-2024 | 1197 | 26/04/2023 | 26/04/2023 | Resource Division | 22.67 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | RADHA KANTAPUR AND IT'S ADJOINING MOUJAS | SM/13034 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RADHA KANTAPUR AND IT'S ADJOINING MOUJAS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001901/2022-2023 | 800/W/MMD | 24/03/2023 | 31/12/2025 | KAMAKSHYA ENTERPRISE | 21.57 | 0 | 0 | 15
4 | PASCHIM MEDINIPUR | Debra | Midnapore Division | RADHA KANTAPUR AND IT'S ADJOINING MOUJAS | SM/13034 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary wall & Providing Functional Household Tap Connection (15,503 Nos.) including 2 years Operation & Maintenance for Baragarh, Benya, Jalimanda, Malihati, Brindabanpur, Satyapur, Nijpapan, Ashari, Radha Kantapur, Chak Narsingha and Bar Jhikuria Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division | ORD/000205/2023-2024 | 2821/MD | 07/08/2023 | 06/10/2025 | GOBINDA MAITY | 4353.07 | 170.56 | 3.92 | 25
Total | [13 empty] | 4403.74 | 176.99 | 4.02