## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Division | RAMCHANDRAPUR AND ITS ADJOINING MOUJAS PWSS | SM/13035 | New | Material Requisition To Resource Division |  |  | RTOR000269/2023-2024 | 2227/MD | 15/06/2023 | 15/06/2023 | Resource Division | 36.62 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | RAMCHANDRAPUR AND ITS ADJOINING MOUJAS PWSS | SM/13035 | New | Electrict quotation bill for TW-I of Ramchandrapur pwss (Ref Consumar ID-204369740),Application No-2004844151,Application Type-New Connection,Name of ccc-Lowada ccc, block-debra |  |  | BILL/02010/2024-2025 | C082430134176 | 20/08/2024 | 20/08/2024 | WBSEDCL | 3.18 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | RAMCHANDRAPUR AND ITS ADJOINING MOUJAS PWSS | SM/13035 | New | Electrict quotation bill for TW-II of Ramchandrapur pwss (Ref Consumar ID-204369742),Application No-2004844160,Application Type-New Connection,Name of ccc-Lowada ccc, block-debra |  |  | BILL/02011/2024-2025 | C082430133485 | 20/08/2024 | 20/08/2024 | WBSEDCL | 3.37 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Debra | Midnapore Division | RAMCHANDRAPUR AND ITS ADJOINING MOUJAS PWSS | SM/13035 | New | Sinking of Tube Well, Laying of Rising Main, Laying distribution pipe line, Pump House, Boundary Wall, 300 cum OHR (Intze type with solid raft) & Accommodate FHTC (1,832 Nos.) including 2 years operation & maintenance under JJM with allied work for Ramchandrapur & its adjoining mouzas W/S Scheme in Debra Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra),JE3 Kharagpur Sub-division | ORD/000279/2023-2024 | 3822/MD | 20/09/2023 | 12/02/2026 | ASIS KUMAR SARANGI | 525.39 | 0 | 0 | 58
5 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | RAMCHANDRAPUR AND ITS ADJOINING MOUJAS PWSS | SM/13035 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RAMCHANDRAPUR AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001603/2022-2023 | 482/W/MMD | 20/03/2023 | 09/08/2025 | SAIKAT SINHA | 23.01 | 0 | 0 | 50
Total | [13 empty] | 591.57 | 0 | 0