## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Division | RELA AND IT'S ADJOINING MOUJAS PWSS | SM/13036 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division |  | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 30/01/2023 | JADAVPUR UNIVERSITY | 100.36 | 0 | 0 | 90
2 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Division | RELA AND IT'S ADJOINING MOUJAS PWSS | SM/13036 | New | Material Requisition To Resource Division |  |  | RTOR000106/2023-2024 | 1298/MD | 28/04/2023 | 28/04/2023 | Resource Division | 23.27 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Mechanical | RELA AND IT'S ADJOINING MOUJAS PWSS | SM/13036 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF RELA PWSS. REF CONSUMER ID-204391648, APPLICATION NO-2004886689, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II |  |  | BILL/02458/2024-2025 | C102401976404 | 03/10/2024 | 03/10/2024 | WBSEDCL | 5.33 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Mechanical | RELA AND IT'S ADJOINING MOUJAS PWSS | SM/13036 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF RELA PWSS. REF CONSUMER ID-204391646, APPLICATION NO-2004886695, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II |  |  | BILL/02464/2024-2025 | C102401976054 | 03/10/2024 | 03/10/2024 | WBSEDCL | 3.68 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Dantan-II | Central Drilling | RELA AND IT'S ADJOINING MOUJAS PWSS | SM/13036 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21472.4 | 0 | 0