## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Division | SATYAPUR AND IT'S ADJOINING MOUJAS PWSS | SM/13038 | New | Material Requisition To Resource Division |  |  | RTOR000049/2023-2024 | 1199 | 26/04/2023 | 26/04/2023 | Resource Division | 13.34 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | SATYAPUR AND IT'S ADJOINING MOUJAS PWSS | SM/13038 | New | Electrict quotation bill for TW-II of Satyapur pwss (Ref Consumar ID-204369741),Application No-2004844164,Application Type-New Connection,Name of ccc-Lowada ccc, block-debra |  |  | BILL/02009/2024-2025 | BP-2024-25-579 | 20/08/2024 | 20/08/2024 | WBSEDCL | 3.31 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | SATYAPUR AND IT'S ADJOINING MOUJAS PWSS | SM/13038 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SATYAPUR AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001602/2022-2023 | 481/W/MMD | 20/03/2023 | 02/09/2025 | SAIKAT SINHA | 23.01 | 0 | 0 | 52
4 | PASCHIM MEDINIPUR | Debra | Midnapore Division | SATYAPUR AND IT'S ADJOINING MOUJAS PWSS | SM/13038 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary wall & Providing Functional Household Tap Connection (15,503 Nos.) including 2 years Operation & Maintenance for Baragarh, Benya, Jalimanda, Malihati, Brindabanpur, Satyapur, Nijpapan, Ashari, Radha Kantapur, Chak Narsingha and Bar Jhikuria Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division | ORD/000205/2023-2024 | 2821/MD | 07/08/2023 | 06/10/2025 | GOBINDA MAITY | 4353.07 | 0 | 0 | 25
Total | [13 empty] | 4392.73 | 0 | 0