## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Rejuvenation of Ground Based Pipe Water Supply Scheme for Palashi & its adjoining mouzas. | SM/13046 | Augmentation | Constructing and fitting fixing MS ladder in diff. level and painting OHR of Palashi and its adjoining mouza water supply scheme within Debra Block under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division |  | ORD/000679/2021-2022 | 109/AE/KSD | 09/03/2022 | 08/04/2022 | GOUTAM PARIA | 4.23 | 4.14 | 97.82 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Rejuvenation of Ground Based Pipe Water Supply Scheme for Palashi & its adjoining mouzas. | SM/13046 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation / Augmentation of existing Palashi PWSS within Debra Block under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division |  | ORD/001007/2021-2022 | 517/MD | 17/03/2022 | 27/03/2022 | GOBINDA MAITY | 2.81 | 2.77 | 98.68 | 100
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Rejuvenation of Ground Based Pipe Water Supply Scheme for Palashi & its adjoining mouzas. | SM/13046 | Augmentation | Electric quotation for PALASHI Water Supply Scheme T/W-(Ref. ID - 204024556) |  |  | BILL/00547/2023-2024 | BP-2023-24-286 | 31/08/2023 | 31/08/2023 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 3.24 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Rejuvenation of Ground Based Pipe Water Supply Scheme for Palashi & its adjoining mouzas. | SM/13046 | Augmentation | Continuation Work Order for the work of Additional Retrofitting to accommodate FHTC under JJM in Palashi Water Supply Scheme, Block: - Debra, District: - Paschim Medinipur within Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE1 Kharagpur Sub-division | ORD/000752/2022-2023 | 709/MD | 06/03/2023 | 20/04/2023 | GOBINDA MAITY | 31.01 | 30.27 | 97.6 | 100
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Rejuvenation of Ground Based Pipe Water Supply Scheme for Palashi & its adjoining mouzas. | SM/13046 | Augmentation | Continuation Work Order for Laying Balance Distribution Pipe line for Rejuvenation of Palashi and its adjoining mouzas Pipe Water Supply Scheme under Debra Block within Midnapore Division, P.H.E. Dte. (Total Length = 6,236.00 Mtr.) | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Debra) | ORD/000053/2023-2024 | 949/MD | 06/04/2023 | 21/05/2023 | MASUM ALI KHAN | 28.34 | 27.77 | 98.02 | 100
6 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Based Pipe Water Supply Scheme for Palashi & its adjoining mouzas. | SM/13046 | Augmentation | Providing and Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring at Tube Well-III of Palashi Water Supply Scheme (Block- Debra) under MMD, PHE Dte., Dist. Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000495/2023-2024 | 1851/W/MMD | 22/08/2023 | 18/02/2024 | RELIABLE CONSTRUCTIONS | 12.83 | 12.28 | 95.68 | 100
7 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Based Pipe Water Supply Scheme for Palashi & its adjoining mouzas. | SM/13046 | Augmentation | New PHE connection at Tw No-III of Palashi PWSS. |  |  | BILL/03228/2023-2024 | BP-2023-24-543 | 11/01/2024 | 11/01/2024 | WBSEDCL | 4.22 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Rejuvenation of Ground Based Pipe Water Supply Scheme for Palashi & its adjoining mouzas. | SM/13046 | Augmentation | Retrofitting to accommodate FHTC under JJM in Palashi W/S Scheme, Block: - Debra, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),JE1 Kharagpur Sub-division | ORD/000262/2020-2021 | 1459/MD | 26/11/2020 | 31/12/2024 | GOBINDA MAITY | 86.73 | 16.82 | 19.39 | 100
9 | PASCHIM MEDINIPUR |  | Midnapore Division | Rejuvenation of Ground Based Pipe Water Supply Scheme for Palashi & its adjoining mouzas. | SM/13046 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall for Rejuvination of Palashi PWSS in Debra Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE1 Kharagpur Sub-division | ORD/000568/2022-2023 | 118/MD | 10/01/2023 | 02/01/2025 | MASUM ALI KHAN | 171.56 | 156.75 | 91.37 | 100
Total | [13 empty] | 344.96 | 250.79 | 72.7