## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Division | TRILOCHANPUR PWSS | SM/13049 | New | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division |  | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 30/01/2023 | JADAVPUR UNIVERSITY | 100.36 | 4.78 | 4.76 | 90
2 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | TRILOCHANPUR PWSS | SM/13049 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for TRILOCHANPUR PWSS Dist-Paschim Medinipur under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001296/2022-2023 | 2299/W/MMD | 29/12/2022 | 27/06/2023 | RITESH ENTERPRISE | 23.01 | 15.96 | 69.38 | 55
3 | PASCHIM MEDINIPUR | Debra | Midnapore Division | TRILOCHANPUR PWSS | SM/13049 | New | Material Requisition To Resource Division |  |  | RTOR000154/2022-2023 | 537/MD | 21/02/2023 | 21/02/2023 | Resource Division | 34.53 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Debra | Midnapore Division | TRILOCHANPUR PWSS | SM/13049 | New | Sinking of Tube well, Laying of Rising main, Pump House, Boundary wall, Construction of 300 CuM OHR (Intze type with solid raft) & Accommodate FHTC (1942 Nos.) including 2 yrs. O & M under JJM with allied work for Trilochanpur PWSS in Debra block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-I] | AE/RWS Midnapore Sub Division |  | ORD/000847/2023-2024 | 824/MD | 15/03/2024 | 11/09/2024 | ASHIM KUMAR DEY | 231.98 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Debra | Midnapore Division | TRILOCHANPUR PWSS | SM/13049 | New | Laying Distribution pipe line under JJM with allied work for Trilochanpur PWSS in Debra block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-II] | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra Blk) | ORD/000008/2024-2025 | 1902/MD | 20/06/2024 | 18/09/2024 | ASHIM KUMAR DEY | 308.72 | 0 | 0 | 0
Total | [13 empty] | 698.6 | 20.74 | 2.97