## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Division | TURKA KASHBA AND IT'S ADJOINING MOUJAS PWSS | SM/13050 | New | Material Requisition To Resource Division |  |  | RTOR000092/2023-2024 | 1291/MD | 28/04/2023 | 28/04/2023 | Resource Division | 29.16 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Mechanical | TURKA KASHBA AND IT'S ADJOINING MOUJAS PWSS | SM/13050 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF TURKA KASHBA PWSS. REF CONSUMER ID-204391652, APPLICATION NO-2004886649, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II |  |  | BILL/02456/2024-2025 | C102401985532 | 03/10/2024 | 03/10/2024 | WBSEDCL | 7.1 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Mechanical | TURKA KASHBA AND IT'S ADJOINING MOUJAS PWSS | SM/13050 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF TURKA KASHBA PWSS. REF CONSUMER ID-204391650, APPLICATION NO-2004886647, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II |  |  | BILL/02455/2024-2025 | C102401986837 | 03/10/2024 | 03/10/2024 | WBSEDCL | 3.46 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Dantan-II | Central Drilling | TURKA KASHBA AND IT'S ADJOINING MOUJAS PWSS | SM/13050 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21379.48 | 0 | 0