## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Division | BRAHMAN KHALISA & ADJOINING MOUZAS | SM/13051 | New | Material Requisition To Resource Division |  |  | RTOR000082/2023-2024 | 1296/MD | 28/04/2023 | 28/04/2023 | Resource Division | 23.21 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Mechanical | BRAHMAN KHALISA & ADJOINING MOUZAS | SM/13051 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF BRAHMAN KHALISA PWSS. REF CONSUMER ID-204373748, APPLICATION NO-2004853061, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II |  |  | BILL/02014/2024-2025 | C082430150750 | 20/08/2024 | 20/08/2024 | WBSEDCL | 3.48 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Mechanical | BRAHMAN KHALISA & ADJOINING MOUZAS | SM/13051 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF BRAHMAN KHALISA PWSS. REF CONSUMER ID-204373752, APPLICATION NO-2004853092, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II |  |  | BILL/02015/2024-2025 | C082430136142 | 20/08/2024 | 20/08/2024 | WBSEDCL | 3.87 | 0 | 0 | 0
Total | [13 empty] | 30.55 | 0 | 0