## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | HARI PURA AND ADJOINING MOUJAS PWSS | SM/13053 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Keshiary Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (1) Bhansra (JL.- 138, Plot-455/738), (2) Gaganeshwar (JL.- 154, Plot- 454), (3) Haripura (JL.- 130, Plot-13), (4) Panchyar (JL.- 194, Plot-400), (5) Santrapur (JL.- 57, Plot-218)] | AE Kharagpur Sub-division |  | ORD/000651/2022-2023 | 746/MD | 13/03/2023 | 12/04/2023 | JADAVPUR UNIVERSITY | 23.9 | 4.78 | 20 | 0
2 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | HARI PURA AND ADJOINING MOUJAS PWSS | SM/13053 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (72023 Nos.) for 41 Nos. PWSS within DANTAN-I, DANTANII & KESHIARY Block Pipe Water Supply Scheme under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),JE RWS Kharagpur Sub-Division( Keshiary),JE RWS Midnapur Sub-Division( Dantan-I),JE2 Kharagpur Sub Division | ORD/000277/2023-2024 | 5056/MD | 26/10/2023 | 30/06/2026 | ENGINEERING PROJECTS (INDIA) LIMITED | 18003.47 | 82.44 | 0.46 | 30
3 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | HARI PURA AND ADJOINING MOUJAS PWSS | SM/13053 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for HARI PURA AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001431/2023-2024 | 3085/W/MMD | 29/11/2023 | 27/05/2024 | M/S EMMESS | 22.79 | 14.69 | 64.46 | 20
4 | PASCHIM MEDINIPUR | Keshiary | Central Drilling | HARI PURA AND ADJOINING MOUJAS PWSS | SM/13053 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 220 Mtrs. Depth) by utilizing Departmental Machineries for Hari Pura W/S Scheme (TW-I & II), Keshiary Block under Paschim Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000082/2023-2024 | 1090/CDD | 18/08/2023 | 01/08/2025 | PADMA ENGINEERING & CO. | 25.33 | 0 | 0 | 100
5 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | HARI PURA AND ADJOINING MOUJAS PWSS | SM/13053 | New | Material Requisition To Resource Division |  |  | RTOR000123/2023-2024 | 1314/MD | 28/04/2023 | 28/04/2023 | Resource Division | 27.15 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | HARI PURA AND ADJOINING MOUJAS PWSS | SM/13053 | New | NAME OF WORK- ELECTRIC QUOTATION BILL FOR TW NO-I OF HARI PURA PWSS, REF CONSUMER ID- 204673226, APPLICATION NO- 2005339386, APPLICATION TYPE- NEW CONNECTION, NAME OF CCC- KESHIARY CCC, NAME OF BLOCK- KESHIARY |  |  | BILL/02188/2025-2026 |  | 20/08/2025 | 20/08/2025 | WBSEDCL | 4.13 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | HARI PURA AND ADJOINING MOUJAS PWSS | SM/13053 | New | NAME OF WORK- ELECTRIC QUOTATION BILL FOR TW NO-II OF HARIPURA PWSS, REF CONSUMER ID- 204735494, APPLICATION NO- 2005482723, APPLICATION TYPE- NEW CONNECTION, NAME OF CCC, KESHIARY CCC, SCHEME CODE- SM/13053, NAME OF BLOCK- KESHIARY. |  |  | BILL/03047/2025-2026 |  | 14/11/2025 | 14/11/2025 | WBSEDCL | 3.82 | 0 | 0 | 0
Total | [13 empty] | 18110.58 | 101.9 | 0.56