## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | HARI PURA AND ADJOINING MOUJAS PWSS | SM/13053 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Keshiary Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (1) Bhansra (JL.- 138, Plot-455/738), (2) Gaganeshwar (JL.- 154, Plot- 454), (3) Haripura (JL.- 130, Plot-13), (4) Panchyar (JL.- 194, Plot-400), (5) Santrapur (JL.- 57, Plot-218)] | AE Kharagpur Sub-division |  | ORD/000651/2022-2023 | 746/MD | 13/03/2023 | 12/04/2023 | JADAVPUR UNIVERSITY | 23.9 | 4.78 | 20 | 0
2 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | HARI PURA AND ADJOINING MOUJAS PWSS | SM/13053 | New | Material Requisition To Resource Division |  |  | RTOR000123/2023-2024 | 1314/MD | 28/04/2023 | 28/04/2023 | Resource Division | 27.15 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | HARI PURA AND ADJOINING MOUJAS PWSS | SM/13053 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for HARI PURA AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001431/2023-2024 | 3085/W/MMD | 29/11/2023 | 27/05/2024 | M/S EMMESS | 22.79 | 14.69 | 64.46 | 20
4 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | HARI PURA AND ADJOINING MOUJAS PWSS | SM/13053 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (72023 Nos.) for 41 Nos. PWSS within DANTAN-I, DANTANII & KESHIARY Block Pipe Water Supply Scheme under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),JE RWS Kharagpur Sub-Division( Keshiary),JE RWS Midnapur Sub-Division( Dantan-I),JE2 Kharagpur Sub Division | ORD/000277/2023-2024 | 5056/MD | 26/10/2023 | 26/03/2026 | ENGINEERING PROJECTS (INDIA) LIMITED | 18003.47 | 93.11 | 0.52 | 30
Total | [13 empty] | 18077.3 | 112.58 | 0.62