## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | HARI PURA AND ADJOINING MOUJAS PWSS | SM/13053 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Keshiary Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (1) Bhansra (JL.- 138, Plot-455/738), (2) Gaganeshwar (JL.- 154, Plot- 454), (3) Haripura (JL.- 130, Plot-13), (4) Panchyar (JL.- 194, Plot-400), (5) Santrapur (JL.- 57, Plot-218)] | AE Kharagpur Sub-division |  | ORD/000651/2022-2023 | 746/MD | 13/03/2023 | 12/04/2023 | JADAVPUR UNIVERSITY | 23.9 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | HARI PURA AND ADJOINING MOUJAS PWSS | SM/13053 | New | Material Requisition To Resource Division |  |  | RTOR000123/2023-2024 | 1314/MD | 28/04/2023 | 28/04/2023 | Resource Division | 27.15 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | HARI PURA AND ADJOINING MOUJAS PWSS | SM/13053 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for HARI PURA AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001431/2023-2024 | 3085/W/MMD | 29/11/2023 | 27/05/2024 | M/S EMMESS | 22.79 | 0 | 0 | 20
4 | PASCHIM MEDINIPUR | Keshiary | Central Drilling | HARI PURA AND ADJOINING MOUJAS PWSS | SM/13053 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 220 Mtrs. Depth) by utilizing Departmental Machineries for Hari Pura W/S Scheme (TW-I & II), Keshiary Block under Paschim Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000082/2023-2024 | 1090/CDD | 18/08/2023 | 01/08/2025 | PADMA ENGINEERING & CO. | 25.33 | 0 | 0 | 100
Total | [13 empty] | 99.16 | 0 | 0