## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-I | Midnapore Division | CHANDABILA & ADJOINING MOUJAS PWSS | SM/13054 | New | Material Requisition To Resource Division |  |  | RTOR000020/2023-2024 | 1152/MD | 25/04/2023 | 25/04/2023 | Resource Division | 18.15 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Garbeta-I | Jhargram Mechanical Division | CHANDABILA & ADJOINING MOUJAS PWSS | SM/13054 | New | new service connection charges at Chandabila-II water supply scheme |  |  | BILL/00597/2024-2025 | 258/JMD | 15/07/2024 | 15/07/2024 | WBSEDCL | 3.61 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Garbeta-I | Jhargram Mechanical Division | CHANDABILA & ADJOINING MOUJAS PWSS | SM/13054 | New | New Service connection charges. |  |  | BILL/01400/2023-2024 | 63/JMD | 13/03/2024 | 13/03/2024 | WBSEDCL | 6.83 | 0 | 0 | 0
Total | [13 empty] | 28.6 | 0 | 0