## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshiary | Central Drilling | KANPUR AND ADJOINING MOUJAS PWSS | SM/13059 | New | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 220 mtrs. Depth) by utilising Departmental machineries for Kanpur W/S Scheme (TW-I & II), Keshiary block under Paschim Midnapur District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000049/2023-2024 | 1091/CDD | 18/08/2023 | 17/09/2023 | M/S B.P.TRADING CORPORATION | 25.33 | 0 | 0 | 100
2 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | KANPUR AND ADJOINING MOUJAS PWSS | SM/13059 | New | Material Requisition To Resource Division |  |  | RTOR000124/2023-2024 | 1315/MD | 28/04/2023 | 28/04/2023 | Resource Division | 27.89 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | KANPUR AND ADJOINING MOUJAS PWSS | SM/13059 | New | Electric quotation bill for Tw No-II of Kanpur PWSS.(ref Consumer ID-204136082) |  |  | BILL/02994/2023-2024 | BP-2023-24-382 | 02/12/2023 | 02/12/2023 | WBSEDCL | 3.01 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | KANPUR AND ADJOINING MOUJAS PWSS | SM/13059 | New | Electric quotation bill for Tw no-I Of Kanpur PWSS.(Ref consumer ID-204136075) |  |  | BILL/03019/2023-2024 | BP-2023-24-380 | 02/12/2023 | 02/12/2023 | WBSEDCL | 3.93 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | KANPUR AND ADJOINING MOUJAS PWSS | SM/13059 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KANPUR AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001678/2023-2024 | 56/W/MMD | 15/01/2024 | 31/03/2025 | ORIENTAL ENGINEERING CO. | 22.86 | 0 | 0 | 20
Total | [13 empty] | 83.03 | 0 | 0