## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | KARANJIMURA AND ADJOINING MOUJAS PWSS | SM/13061 | New | Material Requisition To Resource Division |  |  | RTOR000125/2023-2024 | 1316/MD | 28/04/2023 | 28/04/2023 | Resource Division | 25.89 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Keshiary | Central Drilling | KARANJIMURA AND ADJOINING MOUJAS PWSS | SM/13061 | New | Providing drilling crew and other allied works for construction of Tube Well ( 250mm X150mm X 220 Mtrs. Depth) by utilizing Departmental Machineries for Karanjimura W/S Scheme (T/W-I & II), Keshiary Block under Paschim Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000087/2023-2024 | 1092/CDD | 18/08/2023 | 12/06/2024 | PADMA ENGINEERING & CO. | 25.33 | 22.5 | 88.85 | 100
3 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | KARANJIMURA AND ADJOINING MOUJAS PWSS | SM/13061 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF KARANJIMURA PWSS. REF CONSUMER ID-204283800, APPLICATION NO-2004695735 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY |  |  | BILL/01154/2024-2025 | BP-2024-25-268 | 12/06/2024 | 12/06/2024 | WBSEDCL | 7.94 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | KARANJIMURA AND ADJOINING MOUJAS PWSS | SM/13061 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF KARANJIMURA PWSS. REF CONSUMER ID-204283801, APPLICATION NO-2004695741, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY |  |  | BILL/01153/2024-2025 | BP-2024-25-269 | 12/06/2024 | 12/06/2024 | WBSEDCL | 3.19 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | KARANJIMURA AND ADJOINING MOUJAS PWSS | SM/13061 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (72023 Nos.) for 41 Nos. PWSS within DANTAN-I, DANTANII & KESHIARY Block Pipe Water Supply Scheme under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),JE RWS Kharagpur Sub-Division( Keshiary),JE RWS Midnapur Sub-Division( Dantan-I),JE2 Kharagpur Sub Division | ORD/000277/2023-2024 | 5056/MD | 26/10/2023 | 26/03/2026 | ENGINEERING PROJECTS (INDIA) LIMITED | 18003.47 | 131.18 | 0.73 | 30
6 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | KARANJIMURA AND ADJOINING MOUJAS PWSS | SM/13061 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KARANJIMURA AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001430/2023-2024 | 3084/W/MMD | 29/11/2023 | 01/10/2025 | SUJOY RANJAN BHOWMICK | 21.58 | 14.66 | 67.95 | 20
Total | [13 empty] | 18087.4 | 168.34 | 0.93