## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | BARAKALANKI AND ADJOINING MOUJAS PWSS | SM/13067 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | AE/RWS Midnapore Sub Division |  | ORD/000597/2022-2023 | 396/MD | 02/02/2023 | 03/05/2023 | JADAVPUR UNIVERSITY | 71.69 | 4.78 | 6.67 | 94
2 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | BARAKALANKI AND ADJOINING MOUJAS PWSS | SM/13067 | New | Material Requisition To Resource Division |  |  | RTOR000097/2022-2023 | 188/MD | 16/01/2023 | 16/01/2023 | Resource Division | 16.01 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | BARAKALANKI AND ADJOINING MOUJAS PWSS | SM/13067 | New | Material Requisition To Resource Division |  |  | RTOR000112/2024-2025 | 3448/MD | 25/11/2024 | 25/11/2024 | Resource Division | 12.2 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | BARAKALANKI AND ADJOINING MOUJAS PWSS | SM/13067 | New | Quotation for new power connection at Barakalankai PWSS T/W no - II of Narayangarh block Applocation no - 2004754804 , Ref ID - 204323283 |  |  | BILL/01305/2024-2025 | BP-2024-25-342 | 25/06/2024 | 25/06/2024 | WBSEDCL | 4.75 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | BARAKALANKI AND ADJOINING MOUJAS PWSS | SM/13067 | New | Quotation for new power connection at Barakalankai PWSS T/W no - I of Narayangarh block Applocation no - 2004752560 , Ref ID - 204317453 |  |  | BILL/01306/2024-2025 | BP-2024-25-341 | 25/06/2024 | 25/06/2024 | WBSEDCL | 6.29 | 0 | 0 | 0
Total | [13 empty] | 110.94 | 4.78 | 4.31