## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-III | Midnapore Division | BARAKURYA AND ADJOINING MOUJAS PWSS | SM/13068 | New | Material Requisition To Resource Division |  |  | RTOR000070/2023-2024 | 1214/MD | 27/04/2023 | 27/04/2023 | Resource Division | 19.59 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Garbeta-III | Jhargram Mechanical Division | BARAKURYA AND ADJOINING MOUJAS PWSS | SM/13068 | New | Quotation for new service connection at BARAKURA T/W -I water supply scheme. |  |  | BILL/00229/2024-2025 | 112/JMD | 13/05/2024 | 13/05/2024 | WBSEDCL | 12.13 | 0 | 0 | 0
Total | [13 empty] | 31.72 | 0 | 0