## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | BENUCHA AND ADJOINING MOUJAS PWSS | SM/13069 | New | Laying of Rising main, distribution pipe line & Accommodate FHTC (397 Nos.) including 2 years operation & maintenance under JJM with allied work for Benucha & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000235/2023-2024 | 3005/MD | 21/08/2023 | 20/10/2023 | SUDHAMAY MAJUMDAR | 115.72 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | BENUCHA AND ADJOINING MOUJAS PWSS | SM/13069 | New | Material Requisition To Resource Division |  |  | RTOR000128/2022-2023 | 375/MD | 03/02/2023 | 03/02/2023 | Resource Division | 26.6 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | BENUCHA AND ADJOINING MOUJAS PWSS | SM/13069 | New | Construction of Pump House & Accommodate FHTC (150 Nos.) under JJM with allied work for Benucha & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-F] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000046/2023-2024 | 1429/MD | 04/05/2023 | 03/07/2023 | AJITESH ACHARJEE | 22.19 | 0 | 0 | 30
4 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | BENUCHA AND ADJOINING MOUJAS PWSS | SM/13069 | New | Laying distribution pipe line & Accommodate FHTC (100 Nos.) under JJM with allied work for Benucha & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000047/2023-2024 | 1430/MD | 04/05/2023 | 18/06/2023 | M/S. ZAMAN ENTERPRISE | 24.56 | 0 | 0 | 10
5 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | BENUCHA AND ADJOINING MOUJAS PWSS | SM/13069 | New | Laying distribution pipe line, Boundary wall & Accommodate FHTC (400 Nos.) under JJM with allied work for Benucha & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-D] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000196/2023-2024 | 2810/MD | 07/08/2023 | 06/10/2023 | APURBA PATRA | 86.47 | 0 | 0 | 10
6 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | BENUCHA AND ADJOINING MOUJAS PWSS | SM/13069 | New | Sinking of 2 nos. Tube well under JJM with allied work for Benucha & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000140/2023-2024 | 2624/MD | 24/07/2023 | 23/08/2023 | MASUM CONSTRUCTION | 16.28 | 0 | 0 | 95
7 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | BENUCHA AND ADJOINING MOUJAS PWSS | SM/13069 | New | New service connection charges for Benucha pwss, t/w no.II |  |  | BILL/01372/2023-2024 | 35/JMD | 11/03/2024 | 11/03/2024 | WBSEDCL | 3.22 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Salbani | Central Drilling | BENUCHA AND ADJOINING MOUJAS PWSS | SM/13069 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
9 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | BENUCHA AND ADJOINING MOUJAS PWSS | SM/13069 | New | Construction of 200 cum OHR (Intze type with solid raft) & Accommodate FHTC (400 Nos.) under JJM with allied work for Benucha & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-E] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000552/2024-2025 | 800/MD | 24/03/2025 | 20/09/2025 | M/S BISWANATH CONSTRUCTION | 96.22 | 0 | 0 | 0
Total | [13 empty] | 21731.02 | 0 | 0