## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | BHIKUBAR AND ADJOINING MOUJAS PWSS | SM/13071 | New | Material Requisition To Resource Division |  |  | RTOR000105/2023-2024 | 1284/MD | 28/04/2023 | 28/04/2023 | Resource Division | 39.41 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | BHIKUBAR AND ADJOINING MOUJAS PWSS | SM/13071 | New | Installation of Display Board for JJM work at different Piped Water Supply Scheme under different block within Midnapore Division, PHE Dte. [PART-B] | Assistant Engineer (HQ) |  | ORD/000785/2023-2024 | 507/MD | 27/02/2024 | 08/03/2024 | HIRAK KUMAR GHOSH | 0.96 | 0.96 | 100 | 100
3 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | BHIKUBAR AND ADJOINING MOUJAS PWSS | SM/13071 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of BHIKUBAR PWSS. REF CONSUMER ID-204310423 APPLICATION NO-2004739593 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I |  |  | BILL/01027/2024-2025 | BP-2024-25-206 | 28/05/2024 | 28/05/2024 | WBSEDCL | 0.84 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | BHIKUBAR AND ADJOINING MOUJAS PWSS | SM/13071 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of BHIKUBAR PWSS. REF CONSUMER ID-204310348 APPLICATION NO-2004739394 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I |  |  | BILL/01025/2024-2025 | BP-2024-25-207 | 28/05/2024 | 28/05/2024 | WBSEDCL | 1.23 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Mechanical | BHIKUBAR AND ADJOINING MOUJAS PWSS | SM/13071 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BHIKUBAR AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001735/2022-2023 | 649/W/MMD | 20/03/2023 | 02/04/2025 | M/S. S.R. ENTERPRISE | 32.33 | 22.1 | 68.37 | 30
6 | PASCHIM MEDINIPUR | Dantan-I | Midnapore Division | BHIKUBAR AND ADJOINING MOUJAS PWSS | SM/13071 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (72023 Nos.) for 41 Nos. PWSS within DANTAN-I, DANTANII & KESHIARY Block Pipe Water Supply Scheme under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),JE RWS Kharagpur Sub-Division( Keshiary),JE RWS Midnapur Sub-Division( Dantan-I),JE2 Kharagpur Sub Division | ORD/000277/2023-2024 | 5056/MD | 26/10/2023 | 26/03/2026 | ENGINEERING PROJECTS (INDIA) LIMITED | 18003.47 | 83.57 | 0.46 | 30
Total | [13 empty] | 18078.25 | 106.64 | 0.59