## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshiary | Central Drilling | CHANDANA AND ADJOINING MOUJAS PWSS | SM/13074 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm x 150mm x 220 Mtrs. Depth) by utilising Departmental machineries for Chandana W/S Scheme (T/W-I & II), Keshierya Block under PaschimeMedinipur District, CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000056/2023-2024 | 390/CDD | 18/05/2023 | 17/06/2023 | S.G. ENTERPRISE | 25.39 | 0 | 0 | 100
2 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | CHANDANA AND ADJOINING MOUJAS PWSS | SM/13074 | New | Material Requisition To Resource Division |  |  | RTOR000117/2023-2024 | 1310/MD | 28/04/2023 | 28/04/2023 | Resource Division | 21.97 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | CHANDANA AND ADJOINING MOUJAS PWSS | SM/13074 | New | ADDITIONAL QUOTATION FOR TW NO-I OF CHANDANA PWSS DUE TO SITE CHANGE. APPLICATION TYPE- DEPOSIT WORKS OTHER THAN SERVICE CONNECTION. NAME OF CCC- KESHIARY CCC, NAME OF BLOCK- KESHIARY, REFERENCE ID-860308277, APPLICATION ID-100000116147. |  |  | BILL/02045/2024-2025 | BP-2024-25-606 | 29/08/2024 | 29/08/2024 | WBSEDCL | 3.62 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | CHANDANA AND ADJOINING MOUJAS PWSS | SM/13074 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of CHANDANA PWSS. (Ref Consumer ID-204175251) |  |  | BILL/03445/2023-2024 | BP-2023-24-585 | 25/01/2024 | 25/01/2024 | WBSEDCL | 3.37 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | CHANDANA AND ADJOINING MOUJAS PWSS | SM/13074 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF CHANDANA PWSS. (Ref Consumer ID-204175252) |  |  | BILL/03446/2023-2024 | BP-2023-24-584 | 25/01/2024 | 25/01/2024 | WBSEDCL | 4.03 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | CHANDANA AND ADJOINING MOUJAS PWSS | SM/13074 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for CHANDANA AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001429/2023-2024 | 3083/W/MMD | 29/11/2023 | 31/08/2025 | DIPALI CONSTRUCTION | 21.53 | 0 | 0 | 20
Total | [13 empty] | 79.91 | 0 | 0