## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | GOVINDAPUR BRAHMAN SASAN AND ADJOINING MOUJAS PWSS | SM/13076 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | AE/RWS Midnapore Sub Division |  | ORD/000597/2022-2023 | 396/MD | 02/02/2023 | 03/05/2023 | JADAVPUR UNIVERSITY | 71.69 | 4.78 | 6.67 | 94
2 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | GOVINDAPUR BRAHMAN SASAN AND ADJOINING MOUJAS PWSS | SM/13076 | New | Material Requisition To Resource Division |  |  | RTOR000220/2023-2024 | 1482 | 10/05/2023 | 10/05/2023 | Resource Division | 36.86 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | GOVINDAPUR BRAHMAN SASAN AND ADJOINING MOUJAS PWSS | SM/13076 | New | Quotation for new power connection at Gobindapur PWSS TW - II Under Narayangarh Block Application No - 2004845772 , Ref ID - 204370310 |  |  | BILL/02442/2024-2025 | C092443180598 | 27/09/2024 | 27/09/2024 | WBSEDCL | 4.92 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | GOVINDAPUR BRAHMAN SASAN AND ADJOINING MOUJAS PWSS | SM/13076 | New | Quotation for new power connection at Gobindapur PWSS TW - I Under Narayangarh Block Application No - 2004845774 , Ref ID - 204370304 |  |  | BILL/02447/2024-2025 | C092443178985 | 27/09/2024 | 27/09/2024 | WBSEDCL | 3.31 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | GOVINDAPUR BRAHMAN SASAN AND ADJOINING MOUJAS PWSS | SM/13076 | New | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE1 Kharagpur Sub-division | ORD/000290/2023-2024 | 5049/MD | 25/10/2023 | 11/06/2026 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 173.79 | 2.05 | 41
6 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | GOVINDAPUR BRAHMAN SASAN AND ADJOINING MOUJAS PWSS | SM/13076 | New | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division | ORD/000368/2024-2025 | 1087/MMSD-I | 06/08/2024 | 21/08/2024 | SOUMEN ELECTRIC | 6.62 | 0 | 0 | 50
7 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | GOVINDAPUR BRAHMAN SASAN AND ADJOINING MOUJAS PWSS | SM/13076 | New | Hiring of 1 (One) Motor Cab (Standard) commercial with Catalytic Converter attachment with Bharat Stage as per prevalent application standard compliant new/not older than 30 (thirty) months from the date of 1st registration on daily hire rate basis for 06 (Six) months only having contract carriage permit for plying within West Bengal from the Regional Transport Authority for the use of the Assistant Engineer (H/Q), Midnapore Division, P.H.E. Dte. for the period of 05 (Five) months from 01.01.2025 to 31.05.2025. | Assistant Engineer (HQ) | Junior Engineer (estimating section) | ORD/001086/2024-2025 | 3838/AE/HQ/MD | 27/12/2024 | 27/05/2025 | NAFISA ENTERPRISE | 0.72 | 0 | 0 | 0
Total | [13 empty] | 8622.42 | 178.57 | 2.07