## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | GODAPIASOL AND ADJOINING MOUJAS PWSS | SM/13077 | New | Material Requisition To Resource Division |  |  | RTOR000127/2022-2023 | 374/MD | 03/02/2023 | 03/02/2023 | Resource Division | 24.83 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | GODAPIASOL AND ADJOINING MOUJAS PWSS | SM/13077 | New | New service connection charges for Godapiasal, tw-I w/s scheme |  |  | BILL/01310/2023-2024 | 81/JMD | 12/02/2024 | 12/02/2024 | WBSEDCL | 3.18 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | GODAPIASOL AND ADJOINING MOUJAS PWSS | SM/13077 | New | New service connection charges for Godapiasal, tw-II w/s scheme |  |  | BILL/01304/2023-2024 | 75/JMD | 12/02/2024 | 12/02/2024 | WBSEDCL | 3.58 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Salbani | Central Drilling | GODAPIASOL AND ADJOINING MOUJAS PWSS | SM/13077 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | GODAPIASOL AND ADJOINING MOUJAS PWSS | SM/13077 | New | Sinking of Tube well, Laying of Rising Main, Laying distribution pipe line, Pump House & Accommodate FHTC (437 Nos.) including 2 years operation & maintenance under JJM with allied work for Godapiyasol & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. in Paschim Medinipur District. [PART-A] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000117/2023-2024 | 2492/MD | 17/07/2023 | 04/11/2025 | MIDNAPUR PIPE CONCERN | 154.62 | 0 | 0 | 40
6 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | GODAPIASOL AND ADJOINING MOUJAS PWSS | SM/13077 | New | Construction of Boundary wall, 150 cum OHR (Torch type with solid raft) & Accommodate FHTC (400 Nos.) under JJM with allied work for Godapiyasol & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. in Paschim Medinipur District. [PART-B] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000334/2024-2025 | 3577/MD | 06/12/2024 | 30/05/2026 | MIDNAPUR PIPE CONCERN | 115.89 | 0 | 0 | 0
Total | [13 empty] | 21641.88 | 0 | 0