## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | CHHOTA NAKDANA AND ADJOINING MOUJAS PWSS | SM/13078 | New | Sinking of 2 (Two) Nos. 250 X 150 mm dia. X 180 mtr. Depth deep tube well by direct rotary method Proposed Pipe Water Supply Scheme for Proposed Chhoto Nakdana & its adjoining mouzas PWSS, Block-Garhbeta-II Dist:- Paschim Medinipore under Midnapore Division PHE Dte. [PART-VI] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000005/2023-2024 | 974/MD | 10/04/2023 | 01/05/2023 | ANNAPURNA TUBEWELL WORKS | 17.57 | 16.8 | 95.58 | 100
2 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | CHHOTA NAKDANA AND ADJOINING MOUJAS PWSS | SM/13078 | New | Material Requisition To Resource Division |  |  | RTOR000139/2023-2024 | 1300/MD | 28/04/2023 | 28/04/2023 | Resource Division | 27.76 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Mechanical | CHHOTA NAKDANA AND ADJOINING MOUJAS PWSS | SM/13078 | New | Electric quotation bill for Tw No-I of Chotanakdana water supply scheme.(Ref Id-204061140) |  |  | BILL/01766/2023-2024 | BP-2023-24-185 | 11/08/2023 | 11/08/2023 | WBSEDCL | 3.42 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Mechanical | CHHOTA NAKDANA AND ADJOINING MOUJAS PWSS | SM/13078 | New | Electric quotation bill for Tw No-II of Chhotanakdana water supply scheme.(Ref Id-204061142). |  |  | BILL/01767/2023-2024 | BP-2023-24-186 | 11/08/2023 | 11/08/2023 | WBSEDCL | 5.41 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | CHHOTA NAKDANA AND ADJOINING MOUJAS PWSS | SM/13078 | New | Laying distribution of Pipe line and accommodate FHTC work (320 Nos.) for Proposed Chhoto Nakdana & its adjoining mouzas PWSS, Block-Garhbeta-II Dist:- Paschim Medinipore under Midnapore Division PHE Dte. [PART-V] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000008/2023-2024 | 977/MD | 10/04/2023 | 19/03/2025 | S.T. ENTERPRISE | 95.59 | 86.61 | 90.61 | 70
6 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | CHHOTA NAKDANA AND ADJOINING MOUJAS PWSS | SM/13078 | New | Laying distribution pipe line and Accommodate FHTC (316 Nos.) under JJM with allied work for Proposed Chhoto Nakdana & its adjoining mouzas PWSS, Block-Garhbeta-II Dist:- Paschim Medinipore under Midnapore Division PHE Dte. [PART-III] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000007/2023-2024 | 976/MD | 10/04/2023 | 09/06/2023 | SANJIT SINHA | 49.38 | 26.56 | 53.78 | 70
7 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | CHHOTA NAKDANA AND ADJOINING MOUJAS PWSS | SM/13078 | New | Laying distribution pipe line and Accommodate FHTC (320 Nos.) under JJM with allied work for Proposed Chhoto Nakdana & its adjoining mouzas PWSS, Block-Garhbeta-II Dist:- Paschim Medinipore under Midnapore Division PHE Dte. [PART-II] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000042/2023-2024 | 1386/MD | 02/05/2023 | 01/07/2023 | S.N. ENTERPRISE (PROP. DIBYENDU GUHA) | 76.5 | 50.66 | 66.22 | 66
8 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | CHHOTA NAKDANA AND ADJOINING MOUJAS PWSS | SM/13078 | New | Construction and Commissioning of 250 Cum Capacity (Intze Type with Pile) Over Headed Reservoir, Soil Investigation, Construction of Pump House, Boundary wall, Laying of Rising main, accommodate FHTC (320 Nos.) with 2 years operation & maintenance for Proposed Chhoto Nakdana & its adjoining mouzas PWSS, Block-Garhbeta-II Dist:- Paschim Medinipore under Midnapore Division PHE Dte. [PART-I] | AE Sadar Sub-division |  | ORD/000042/2024-2025 | 2257/MD | 23/07/2024 | 19/01/2025 | M/S R.N. ENTERPRISE | 136.16 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Garbeta-II | Central Drilling | CHHOTA NAKDANA AND ADJOINING MOUJAS PWSS | SM/13078 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 18.1 | 0.08 | 11
10 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | CHHOTA NAKDANA AND ADJOINING MOUJAS PWSS | SM/13078 | New | Laying distribution of Pipe line, Construction of Pump House, Boundary wall and Accommodate FHTC work (360 Nos.) for Proposed Chhoto Nakdana & its adjoining mouzas PWSS, Block-Garhbeta-II Dist:- Paschim Medinipore under Midnapore Division PHE Dte. [PART-IV] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000055/2024-2025 | 2578/MD | 22/08/2024 | 20/12/2024 | S.N ENTERPRISE | 95.96 | 0 | 0 | 0
Total | [13 empty] | 21847.52 | 198.72 | 0.91