## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshiary | Central Drilling | DAKSHINDIHA AND ADJOINING MOUJAS PWSS | SM/13079 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm x 150mm x 220Mtrs. Depth) by utilising Departmental for Dakshindiha W/S Scheme (T/W- I & II) , Keshiarya block under Paschim Medinipur District, CDD PHE Dte | Driller In Charge | Junior Engineer | ORD/000062/2023-2024 | 391/CDD | 18/05/2023 | 17/06/2023 | PADMA ENGINEERING & CO. | 25.43 | 0 | 0 | 100
2 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | DAKSHINDIHA AND ADJOINING MOUJAS PWSS | SM/13079 | New | Material Requisition To Resource Division |  |  | RTOR000120/2023-2024 | 1312/MD | 28/04/2023 | 28/04/2023 | Resource Division | 25.9 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | DAKSHINDIHA AND ADJOINING MOUJAS PWSS | SM/13079 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DAKSHINDIHA AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001428/2023-2024 | 3082/W/MMD | 29/11/2023 | 27/05/2024 | CONCORD ENGINEERING | 21.56 | 0 | 0 | 30
4 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | DAKSHINDIHA AND ADJOINING MOUJAS PWSS | SM/13079 | New | ELECTRIC QUOTATION BILL TW NO-I of DAKHINDIHA PWSS. REF CONSUMER ID-204204413, APPLICATION NO-2004578886, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY |  |  | BILL/03582/2023-2024 | BP-2023-24-633 | 08/02/2024 | 08/02/2024 | WBSEDCL | 2.9 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | DAKSHINDIHA AND ADJOINING MOUJAS PWSS | SM/13079 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of DAKHINDIHA PWSS. REF CONSUMER ID-204204414, APPLICATION NO-2004578903, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY |  |  | BILL/03581/2023-2024 | BP-2023-24-632 | 08/02/2024 | 08/02/2024 | WBSEDCL | 3.04 | 0 | 0 | 0
Total | [13 empty] | 78.84 | 0 | 0